# MCA 805: Operational

# Research and Project

# Management

| Developer: | Richard K. Siele, PhD |
| --- | --- |
| Programme: | Master of Commerce |

PURPOSE OF THE COURSE This course aims to provide students with a comprehensive understanding of the principles and techniques of operations research (OR) and their application in project management. By integrating OR methodologies with project management principles, students will learn how to optimize project processes, resources, and decision-making to achieve project objectives efficiently. EXPECTECTED LEARNING OUTCOMES Upon completion of this course, students should be able to: - Demonstrate proficiency in applying operations research techniques to optimize project processes and resource allocation. - Analyze project data using quantitative methods in linear programming, simulation to support informed decision-making. - Evaluate the impact of integrating operations research principles into project management practices on project performance and success. - Design operations research models to solve real-world project management problems effectively COURSE CONTENT

Introduction to Operations Research and Project Management; Overview of operations research principles and their relevance to project management, Integration of operations research techniques in project planning and execution. Linear Programming and Project Resource Allocation; Principles of linear programming and its application in optimizing project resource allocation, Case studies demonstrating the use of linear programming in project management. Network Analysis and Project Scheduling; Introduction to Techniques, PERT technique in analysis and scheduling, CPM technique for project scheduling, critical path analysis, Application of network analysis in project time management and scheduling optimization. Simulation Modelling in Project Risk Analysis; Simulation techniques for analyzing project risks and uncertainties, Utilization of simulation modelling to assess project risk and develop mitigation strategies. Decision Analysis in Project Decision-making; Principles of decision analysis and decision trees in project decision-making, Case studies illustrating the use of decision analysis in project risk assessment and decision-making. Queuing Theory and Project Process Optimization; Queuing theory fundamentals and its application in optimizing project processes, Implementation of queuing models to improve project workflow and resource utilization, Inventory Management Techniques in Project Procurement, Inventory management principles and their relevance to project procurement, Application of inventory management techniques to optimize project procurement processes. Multi-criteria Decision Making in Project Selection; Multi-criteria decision-making methods for project selection and prioritization.; Evaluation of project alternatives using multi-criteria decision-making models. Optimization Models in Project Portfolio Management; Optimization models for project portfolio selection and management, Integration of optimization techniques in project portfolio optimization strategies. Applications of Operations Research in Real-world Project Management; Case studies and applications demonstrating the use of operations research in various project management contexts, Emerging trends and future directions in operations research and project management.

LIST MODULES - Introduction to Operations Research and Project Management - Linear Programming and Project Resource Allocation - Network Analysis and Project Scheduling - Simulation Modelling in Project Risk Analysis - Decision Analysis in Project Decision-making - Queuing Theory and Project Process Optimization - Multi-criteria Decision Making in Project Selection - Optimization Models in Project Portfolio Management - Applications of Operations Research in Real-world Project Management

# TABLE OF CONTENTS

TABLE OF CONTENTS	4

MODULE 1: Introduction to Operations Research and Project Management	8

Module Overview	8

Learning Outcomes	8

Learning Activities/Task List	8

INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES	9

MASTERY EXERCISE 1.1	12

VIDEO 3 (Youtube, please include link)	14

QUIZ/ Questions	14

READING MATERIAL 1	15

ACTIVITY 3: PRACTICAL/MINIPROJECT/WORKSHOP	17

VIDEO 1: Demonstration of practical use of knowledge acquired	17

REFERENCE LIST AND FURTHER READING	18

END OF MODULE ASSESSMENT 1.1	18

TAKE HOME MESSAGE/SELF REFLECTION	19

WHAT’S NEXT?	19

MODULE 2: Linear Programming and Project Resource Allocation	20

Module Overview	20

Learning Outcomes	20

Learning Activities/Task List	21

INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES	21

MASTERY EXERCISE 1.1	22

PRE-RECORDED LECTURE ON TOPIC	24

VIDEO 3 (Youtube, please include link)	27

QUIZ/ Questions	28

READING MATERIAL 1	29

ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP	29

VIDEO 1: Demonstration of practical use of knowledge acquired	29

REFERENCE LIST AND FURTHER READING	30

END OF MODULE ASSESSMENT 1.2	30

TAKE HOME MESSAGE/SELF REFLECTION	32

WHAT’S NEXT?	32

MODULE 3: Network Analysis and Project Scheduling	33

Module Overview	33

Learning Outcomes	33

Learning Activities/Task List	33

INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES	34

MASTERY EXERCISE 1.1	38

PRE-RECORDED LECTURE ON TOPIC	41

VIDEO 3 (Youtube, please include link)	43

QUIZ/ Questions	46

READING MATERIAL 1	47

ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP	48

VIDEO 1: Demonstration of practical use of knowledge acquired	48

REFERENCE LIST AND FURTHER READING	49

END OF MODULE ASSESSMENT 1.3	49

TAKE HOME MESSAGE/SELF REFLECTION	50

WHAT’S NEXT?	50

MODULE 4: SIMULATION MODELLING IN PROJECT RISK ANALYSIS	51

Module Overview	51

Learning Outcomes	51

Learning Activities/Task List	51

INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES	51

MASTERY EXERCISE 1.1	53

PRE-RECORDED LECTURE ON TOPIC	54

Lecture on Simulation Modelling in Project Risk Analysis	54

VIDEO 3 (Youtube, please include link)	54

QUIZ/ Questions	54

READING MATERIAL 1	55

ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP	55

VIDEO 1: Demonstration of practical use of knowledge acquired	55

REFERENCE LIST AND FURTHER READING	56

END OF MODULE ASSESSMENT 1.2	57

TAKE HOME MESSAGE/SELF REFLECTION	58

WHAT’S NEXT?	58

MOCDULE 5:	Decision Analysis in Project Decision-making	59

Module Overview	59

Learning Outcomes	59

Learning Activities/Task List	59

INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES	60

ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP	64

REFERENCE LIST AND FURTHER READING	65

TAKE HOME MESSAGE/SELF REFLECTION	66

MODULE 6: Queuing Theory and Project Process Optimization	67

Learning Outcomes	67

Learning Activities/Task List	68

INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES	68

MASTERY EXERCISE 1.1	69

ACTIVITY 3: PRACTICAL / MINI-PROJECT/ WORKSHOP	71

REFERENCE LIST AND FURTHER READING	71

TAKE HOME MESSAGE/SELF REFLECTION	72

MODULE 7: Multi-criteria Decision Making in Project Selection	73

Module Overview	73

Learning Outcomes	73

Learning Activities/Task List	73

INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES	74

MASTERY EXERCISE 1.1	77

ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP	80

REFERENCE LIST AND FURTHER READING	81

TAKE HOME MESSAGE/SELF REFLECTION	82

MODULE 8: Optimization Models in Project Portfolio Management	83

Module Overview	83

Learning Outcomes	83

Learning Activities/Task List	84

INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES	84

MASTERY EXERCISE 1.1	86

ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP	92

REFERENCE LIST AND FURTHER READING	92

TAKE HOME MESSAGE/SELF REFLECTION	95

MODULE 9: Applications of Operations Research in Real-world Project Management	96

Module Overview	96

Learning Outcomes	96

Learning Activities/Task List	96

INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES	97

MASTERY EXERCISE 1.1	100

ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP	105

REFERENCE LIST AND FURTHER READING	105

TAKE HOME MESSAGE/SELF REFLECTION	107

# MODULE 1: Introduction to Operations Research and Project Management

INSTRUCTIONAL HOURS: 4

### Module Overview

In this module, you will learn an in-depth overview of key principles in operations research (OR) and their critical relevance to project management. It explores how OR techniques such as mathematical modeling, statistical analysis, and optimization are integrated into various phases of project planning and execution. Students will learn how to apply these techniques to improve decision-making, resource allocation, risk management, and overall project efficiency. By linking OR methodologies with project management frameworks, the module equips learners with advanced tools for tackling complex, real-world challenges in both operational and strategic contexts.

### Learning Outcomes

By the end of this module, you should be able to:

- Demonstrate a comprehensive understanding of key operations research (OR) principles and their application to project management contexts.

- Apply Operation Research techniques such as optimization, simulation, and decision analysis to enhance project planning and execution strategies.

- Analyze and solve complex project management problems using quantitative methods from operations research.

- Integrate operations research methodologies into project risk management, resource allocation, and performance evaluation for improved project outcomes.

### Learning Activities/Task List

- Watch Lecture Video

- Review power presentation PDF

- Watch lecture related videos

- Complete participation assignment:  Quiz 1

- Review concept assignments: Quiz 2

## INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES

|  | (Learners to engage in self-directed learning READING MATERIAL 1 (Notes, presentation, an article, a book chapter, case study, video, please add assessment…) |
| --- | --- |

Task 1: Read the provided lecture notes

OPERATION RESEARCH AND PROJECT MANAGEMENT

Operations Research (OR) is a discipline that applies advanced analytical methods to help make better decisions. It uses mathematical modeling, statistical analysis, and optimization techniques to solve complex decision-making problems. OR emerged during World War II to address logistical and military problems and has since expanded into diverse fields such as business, engineering, healthcare, and project management.

Example 1.1

Describe the key principles of Operations Research and explain their relevance to effective Project Management. Provide examples of how Operations Research techniques can be used to improve decision-making in project planning and execution.

#### Rubrics 1.1:

Operations Research (OR) is a discipline that applies advanced analytical methods to help make better decisions. It plays a critical role in optimizing resources, processes, and outcomes in various fields, including project management. Below are the key principles of Operations Research and their relevance to effective project management:

#### 1. Optimization

- Principle: Optimization involves finding the best solution from a set of feasible solutions by maximizing or minimizing an objective function. In project management, this often refers to optimizing resources, costs, and timelines.

- Relevance: Project managers frequently face the challenge of balancing competing demands, such as time, cost, and quality. Optimization techniques, such as linear programming, can help identify the most efficient use of resources to meet project objectives within constraints like budget and time.

- Example: A project manager can use linear programming to optimize resource allocation across multiple tasks while ensuring that critical milestones are met on time. For instance, assigning workers to tasks in a way that minimizes overall project duration.

#### 2. Modeling

- Principle: Modeling is the process of representing a real-world problem in mathematical terms. It helps simplify complex systems for analysis, enabling managers to understand the relationships between different variables and constraints.

- Relevance: In project management, models provide a structured way to represent project activities, timelines, and dependencies. This facilitates better planning, scheduling, and risk assessment.

- Example: A project network diagram (like PERT or CPM) is a model that represents the sequence of activities in a project, highlighting the critical path and helping managers identify where delays may impact overall project completion.

#### 3. Simulation

- Principle: Simulation involves creating a virtual model of a system or process and experimenting with it to understand its behavior under various conditions. Simulations allow project managers to evaluate different scenarios without physically implementing changes.

- Relevance: Project managers can use simulation techniques to assess risks, predict project outcomes, and evaluate the impact of potential decisions on the project schedule and costs.

- Example: Monte Carlo simulation is commonly used to model the uncertainty in project scheduling by simulating the effects of various risk factors on project completion times, giving project managers a probabilistic understanding of the schedule.

#### 4. Decision Analysis

- Principle: Decision analysis involves the use of quantitative methods, such as decision trees and payoff matrices, to evaluate alternative courses of action in decision-making. It is particularly useful in situations with uncertainty and multiple conflicting objectives.

- Relevance: In project management, decision analysis helps managers weigh different project strategies, assess risks, and make informed decisions by comparing potential outcomes and their associated probabilities.

- Example: A project manager might use a decision tree to evaluate whether to hire additional workers or extend deadlines based on the likelihood of finishing the project on time and the associated costs.

#### 5. Queueing Theory

- Principle: Queueing theory studies waiting lines and can be applied to optimize processes where resources are limited, and there is a need to manage demand and capacity effectively.

- Relevance: In project management, queueing theory helps in resource management, especially when tasks must wait for resources, such as equipment or personnel, which are shared across multiple activities.

- Example: A project manager can apply queueing theory to determine the optimal number of machines or workers needed to minimize downtime and ensure smooth project execution, especially in construction or manufacturing projects.

#### 6. Inventory Management

- Principle: Inventory management techniques focus on controlling the amount of inventory held at any point in time to minimize costs while meeting project demand.

- Relevance: In projects involving large material requirements, such as construction or product development, inventory management ensures that materials are available when needed, without holding excessive stock that increases costs.

- Example: A project manager might use the Economic Order Quantity (EOQ) model to determine the optimal order size for raw materials, balancing the costs of ordering and holding inventory to avoid delays and extra expenses.

### Application of Operations Research Techniques in Project Planning and Execution

#### 1. Project Scheduling and Time Optimization (CPM and PERT)

- CPM (Critical Path Method) and PERT (Program Evaluation and Review Technique) are key OR techniques that aid in scheduling and optimizing project timelines.

- Example: A project manager uses CPM to identify the critical path in a construction project, ensuring that resources are allocated to critical tasks to avoid delays in project completion. PERT, with its focus on probabilistic time estimates, helps in managing projects with uncertainty in task durations.

#### 2. Resource Allocation (Linear Programming)

- Linear programming helps in allocating limited resources such as manpower, materials, and time to maximize project outputs or minimize costs.

- Example: In a software development project, linear programming can be used to assign developers to different modules based on their skills and the time required to complete each module, ensuring the project is completed as quickly as possible with the available team.

#### 3. Risk Analysis and Decision Support (Monte Carlo Simulation)

- Monte Carlo simulation allows project managers to model uncertainty in project parameters and assess the impact of risks on project outcomes.

- Example: A project manager running a Monte Carlo simulation can predict the likelihood of completing a project within budget given the potential for cost overruns in certain tasks, thereby making more informed decisions regarding contingency planning.

#### Task 2: Attempt this exercise: MASTERY EXERCISE 1.1

Attempt the following question:

Discuss how Operations Research techniques can be integrated into project planning and execution phases. Analyze the role of techniques such as linear programming, simulation, and Critical Path Method (CPM) in optimizing project schedules, resources, and costs.

|  | other materials or Icons to be used (use as appropriate) |
| --- | --- |

|  | PRE-RECORDED LECTURE ON TOPIC |
| --- | --- |

Task 3: You are provided with this pre-recorded video which you need to listen to: Video on Introduction to Operations Research and Project Management:

"Hello everyone, and welcome to this session on Operations Research and Project Management. Today, we'll explore how Operations Research, or OR, principles can be applied to enhance the efficiency and effectiveness of project management. By the end of this lecture, you should be able to:

- Understand the core principles of Operations Research.

- Recognize the relevance of these principles to project management.

- Identify key OR techniques and how they are integrated into project planning and execution."

Slide 3: Overview of Operations Research (OR) Instructor: "Operations Research is the application of analytical methods to help make better decisions. It relies on mathematical models, statistical analysis, and optimization techniques to solve complex problems, particularly in decision-making environments with multiple objectives and constraints. OR plays a critical role in various fields, from supply chain management to transportation, healthcare, and, of course, project management."

Slide 4: Key Principles of Operations Research Instructor: "Let’s break down some of the key principles of OR:

- Optimization: This involves finding the best solution from a set of available options, considering constraints like time, resources, or cost.

- Mathematical Modeling: This is the foundation of OR, where we create mathematical representations of real-world systems to understand and analyze them.

- Simulation: This technique models complex systems to study their behavior over time, especially when uncertainty or variability is involved.

- Queuing Theory: Queuing theory helps us analyze waiting lines and optimize processes to reduce delays.

- Network Analysis: Often used to study systems like supply chains or communication networks, this approach models interconnected systems as networks of nodes and links."

Slide 5: Relevance of OR to Project Management Instructor: "Now, how does this relate to project management? Well, project managers constantly face decisions involving resource allocation, scheduling, budgeting, and risk management. OR offers tools to optimize these decisions by providing quantitative methods that can handle the complexity of project environments.

For example:

- Resource Allocation: OR techniques like linear programming can help assign resources efficiently across tasks.

- Risk Management: Simulation models allow project managers to anticipate potential risks and prepare for different scenarios.

- Scheduling: Network analysis tools like the Critical Path Method (CPM) help ensure that project timelines are optimized."

Slide 6: Integration of OR Techniques in Project Planning Instructor: "Let’s look at how OR techniques are integrated into the different phases of project management, starting with the planning phase. In this phase, project managers must determine the best way to allocate resources, forecast demand, and create schedules. OR techniques offer powerful solutions here:

- Linear Programming (LP) is one such technique used for resource scheduling. It can help you find the best allocation of limited resources to different tasks while minimizing costs or maximizing efficiency.

- Dynamic Programming is another technique that breaks a large problem into smaller, manageable subproblems, making it easier to optimize project schedules."

Example:
"A project manager could use integer programming to determine the optimal number of workers to assign to various tasks, ensuring the project remains on schedule without exceeding budget limits."

Slide 7: OR Techniques in Project Execution Instructor: "In the execution phase of project management, OR techniques continue to play a vital role. Two critical techniques are:

- Simulation Modeling, which allows project managers to model various 'what-if' scenarios, such as delays in supply deliveries or equipment failures. This helps in developing contingency plans.

- Critical Path Method (CPM) is used to identify the most critical tasks that must be completed on time for the project to remain on schedule.

Example:
"A project manager working on a construction project might use CPM to track which tasks—like laying the foundation or installing electrical systems—are most time-sensitive. By identifying these critical tasks, the manager can allocate additional resources to ensure they are completed on time."

Slide 8: Optimizing Resources and Costs with OR Instructor: "One of the greatest strengths of Operations Research is its ability to optimize resource allocation and minimize costs. Using techniques like linear programming and simulation, project managers can determine the most cost-effective ways to complete tasks, allocate materials, and schedule activities.

Example:
"In an IT project, you could use OR to determine the most efficient allocation of technical staff to tasks based on their expertise, ensuring no time is wasted and the project stays within budget."

Slide 9: Case Study – OR in a Large Construction Project Instructor: "Let’s walk through a quick case study. Imagine you are managing a large construction project, and you have to ensure the project is completed within a set budget and timeline. How could OR help?

- CPM: You use CPM to determine the critical tasks, like excavation and foundation work, that have to be completed on time.

- Linear Programming: This is applied to allocate the optimal number of workers and machinery to different tasks, balancing costs with efficiency.

- Simulation: By simulating potential risks like adverse weather or equipment failure, you develop contingency plans that keep the project on track, even if things don’t go as expected."

"This combination of OR techniques enables you to optimize time, resources, and costs, ensuring the project is both efficient and profitable."

Slide 10: Conclusion Instructor: "To summarize, Operations Research provides powerful tools that can significantly enhance decision-making in project management. From optimizing resource allocation to risk management and scheduling, OR techniques like linear programming, simulation, and network analysis help project managers handle complexity and uncertainty with confidence.

I encourage you to explore these techniques further and think about how they might apply to your own projects or professional experiences."

Slide 11: Thank You and Next Steps Instructor: "Thank you for joining this session! In our next lecture, we will dive deeper into specific OR techniques like Linear Programming and Dynamic Programming, with examples of their application in real-world project management. Feel free to reach out with any questions, and I look forward to seeing you in the next class."

|  | #### VIDEO 3 (Youtube, please include link) |
| --- | --- |

Task 4: Here is a video on “Introduction to Operations Research - History, OR Today, Models, Structure, & Phases of OR”. The video is 7.25 mins; click the link below and listen.

https://youtu.be/llqhvtxr9U4?si=0Caz9m_81oziKlf8

Having listened to the video on financially stressed, attempt the following:

Quiz:

Discuss how operation research can be applied in solving today’s business challenges.

|  | #### QUIZ/ Questions |
| --- | --- |

Task 5: Attempt all these questions:

Question 1: Which of the following is a key principle of Operations Research that helps in optimizing decision-making processes in project management?

A) Brainstorming
B) Mathematical Modeling
C) Stakeholder Analysis
D) Qualitative Research

Question 2: Which Operations Research technique is most commonly used to determine the shortest path or critical activities that must be completed on time to avoid project delays?

A) Simulation
B) Critical Path Method (CPM)
C) Queuing Theory
D) Dynamic Programming

Question 3: How does linear programming contribute to project management?

A) It helps project managers visualize risks.
B) It allows for optimal allocation of resources while adhering to project constraints.
C) It monitors project performance in real-time.
D) It determines the order in which project tasks should be completed.

|  | #### READING MATERIAL 1 |
| --- | --- |

Task 6: Read chapter 1 on Historical Development on page 31-40.

Ramady P. M. (2008). Operations Research: An Introduction (2nd ed.). New Age International Publishers pg 1-40.

After reading this material, attempt the following question:

Quiz:

Trace the history of Operations Research (5marks)

Rubrics

History of Operations Research (OR)

Operations Research (OR) has its roots in military strategy and resource optimization. It emerged as a formal discipline during World War II when the British military sought ways to efficiently use limited resources such as radar, aircraft, and manpower. The key milestones in the development of OR are as follows:

- Origins in World War II (1939-1945):

  - The term "Operations Research" was coined in Britain during World War II when interdisciplinary teams of scientists, mathematicians, and engineers were tasked with improving military operations. One of the early successes of OR was optimizing radar usage and improving anti-submarine tactics. This collaborative effort helped military forces make data-driven decisions to maximize the effectiveness of available resources.

  - The work done by these scientists involved the application of mathematical models and statistical methods to solve complex operational problems. These models helped in optimizing logistics, resource allocation, and decision-making under uncertainty.

- Post-World War II Developments:

  - After the war, the success of OR in military applications attracted interest from industrial and business sectors. Many of the methods developed during the war were adapted for use in peacetime industries such as manufacturing, transportation, and healthcare.

  - The U.S. military also adopted OR extensively, particularly for logistics, weapons development, and supply chain optimization during the Cold War. The growth of OR in the U.S. was largely influenced by the establishment of RAND Corporation, an institution dedicated to research and analysis.

- Development of Key Techniques (1940s-1960s):

  - The field of OR saw the development of important techniques such as linear programming, developed by George Dantzig in 1947. Linear programming became one of the most widely used tools in OR for solving optimization problems involving constraints.

  - Other techniques such as game theory (developed by John von Neumann and Oskar Morgenstern), queuing theory, simulation, and inventory control models were also introduced during this period.

- Growth and Expansion (1960s-Present):

  - OR expanded from military and industrial applications to a wide range of fields including healthcare, finance, transportation, and project management. The rise of computers and digital technology in the 1960s further revolutionized the field by allowing more complex and large-scale problems to be solved efficiently.

  - Today, OR is used in various sectors such as logistics (supply chain management), telecommunications, finance, marketing, and energy management. It plays a critical role in decision-making processes, particularly for optimizing processes, improving resource allocation, and reducing costs.

- Modern Applications and Integration:

  - Modern OR integrates data analytics, machine learning, and advanced computational techniques to solve contemporary problems. It combines both theoretical and applied research to tackle issues such as urban planning, disaster management, healthcare optimization, and environmental sustainability.

In summary, Operations Research began as a military tool during World War II but has since evolved into a key discipline that enhances decision-making in both private and public sectors through mathematical models and scientific analysis.

## ACTIVITY 3: PRACTICAL/MINIPROJECT/WORKSHOP

|  | #### VIDEO 1: Demonstration of practical use of knowledge acquired |
| --- | --- |

.

Task 7: Here is a practical demonstration of how the knowledge of Operations Research can be used in organizations. The video is 4.49 mins; click the link below and listen.

https://youtu.be/_zhtDJX3kOY?si=24pJKihMpMaWlgFl

What have you learnt after listening to this video?

|  | ONLINE DISCUSSION Use chats, forums, journals, wikis, blogs, question/answer, message my teacher to engage others. |
| --- | --- |

Task 8: Attempt the following question:

Form a group of not less than two learners and discuss this scenario: A large hospital is trying to improve the efficiency of its emergency room (ER) operations. The hospital deals with an average of 300 patients per day. Due to resource constraints (staffing, rooms, equipment), patient waiting times have increased, and patient satisfaction has dropped. The hospital wants to optimize the allocation of resources (e.g., nurses, doctors, and medical equipment) to minimize patient wait times while ensuring that each patient receives the appropriate level of care.

Develop an Operations Research model to help the hospital optimize the scheduling and allocation of resources in the ER. Your model should:

- Minimize the total patient waiting time.

- Ensure that critical patients (e.g., trauma cases) receive immediate attention.

- Allocate staff efficiently to different shifts based on patient arrival patterns.

- Consider different constraints, including staff availability, room capacity, and varying levels of patient severity.

Required:

- Formulate the problem using linear programming (or another appropriate optimization technique).

- Specify the decision variables, objective function, and constraints.

- Solve the model using a suitable software package (e.g., Gurobi, Lingo, or Excel Solver) and analyze the results.

- Propose actionable recommendations for the hospital management to improve ER efficiency.

## REFERENCE LIST AND FURTHER READING

- Hillier, F. S., & Lieberman, G. J. (2010). Introduction to Operations Research (9th ed.). McGraw-Hill Education.

- Winston, W. L. (2020). Operations Research: Applications and Algorithms (4th ed.). Cengage Learning.

- Meredith, J. R., Shafer, S. M., & Mantel, S. J. (2020). Project Management: A Managerial Approach (10th ed.). Wiley.

- Taha, H. A. (2017). Operations Research: An Introduction (10th ed.). Pearson Education.

### END OF MODULE ASSESSMENT

Tsk 9: Attempt this question which will be used in assessing your performance for this module:

Question:

A company is managing a large-scale construction project with multiple phases and limited resources. The project manager is considering using Operations Research (OR) techniques to improve project planning and execution. Your task is to evaluate how OR principles can be integrated into the project management process to optimize resource allocation, scheduling, and risk management.

Required: Discuss how Operations Research principles can be applied to improve the efficiency of project management in the context of this construction project. Provide specific examples of OR techniques that could be utilized in project planning and execution. In your answer, address the following:

- Overview of Operations Research Principles:

  - What are the core principles of Operations Research?

  - How do these principles apply to project management?

- Integration of OR Techniques in Project Management:

  - Describe at least three OR techniques that can be applied to project planning and execution.

  - How would each technique address specific challenges in the construction project?

- Practical Implications:

  - What are the potential benefits of integrating OR techniques into the project management process?

  - Discuss any limitations or considerations that the project manager should be aware of when implementing these techniques.

Rubrics:

- Overview of Operations Research Principles (25 points):

  - Excellent (22-25 points): Thoroughly explains core OR principles with clear and relevant examples. Provides a strong connection between OR principles and project management.

  - Good (17-21 points): Adequately explains OR principles with relevant examples. Shows a good connection to project management.

  - Fair (12-16 points): Provides a basic explanation of OR principles with some relevance to project management. Examples may be limited or unclear.

  - Poor (0-11 points): Inadequate explanation of OR principles with minimal or unclear relevance to project management.

- Integration of OR Techniques in Project Management (35 points):

  - Excellent (31-35 points): Clearly describes and applies at least three OR techniques with detailed examples. Demonstrates a deep understanding of how each technique addresses specific project challenges.

  - Good (24-30 points): Describes and applies three OR techniques with relevant examples. Shows a good understanding of how the techniques address project challenges.

  - Fair (17-23 points): Describes and applies OR techniques with limited examples. The explanation of how the techniques address project challenges is basic.

  - Poor (0-16 points): Inadequate description or application of OR techniques with minimal or unclear examples. Limited understanding of how techniques address project challenges.

- Practical Implications (20 points):

  - Excellent (18-20 points): Insightful discussion on the benefits and limitations of OR techniques. Provides practical recommendations and considerations for implementation.

  - Good (14-17 points): Discusses benefits and limitations with some practical recommendations and considerations.

  - Fair (10-13 points): Basic discussion on benefits and limitations with limited practical recommendations.

  - Poor (0-9 points): Minimal or unclear discussion on benefits and limitations. Lacks practical recommendations.

- Clarity and Organization (20 points):

  - Excellent (18-20 points): Well-organized and clearly written response with logical flow. Excellent grammar and spelling.

  - Good (14-17 points): Organized response with minor issues in clarity or flow. Good grammar and spelling.

  - Fair (10-13 points): Some issues with organization, clarity, or flow. Noticeable grammar and spelling errors.

  - Poor (0-9 points): Disorganized or unclear response with significant grammar and spelling errors.

## TAKE HOME MESSAGE/SELF REFLECTION

Task 10: After going through Introduction to Operation Research and Project Management, how can you apply this real-world life situations?

### WHAT’S NEXT?

- Chapter 1 Review Assignment

- Module 2

- Linear Programming and Project Resource Allocation

- HACCP Review

# MODULE 2: Linear Programming and Project Resource Allocation

INSTRUCTIONAL HOURS: 4

### Module Overview

In this module, you'll learn about the principles of linear programming and its practical application in optimizing project resource allocation. You will learn how to model and solve linear programming problems, with a focus on maximizing or minimizing key project objectives such as cost, time, or resource use, while adhering to constraints like budgets, deadlines, and workforce limitations. Through case studies, you will examine real-world applications in project management, such as optimizing resource distribution in construction projects, minimizing operational costs, and streamlining project schedules in IT and manufacturing sectors. By the end of the module, you will be equipped with the tools to apply linear programming techniques for efficient decision-making and resource optimization in complex project environments.

### Learning Outcomes

By the end of this module, you should be able to:

- Formulate and solve optimization problems in project management, with a focus on resource allocation.

- Develop linear programming models that address project constraints such as budget, time, and resource availability, to optimize project outcomes.

- Analyze and interpret case studies that demonstrate the application of linear programming in various industries, identifying key factors that contribute to successful project resource optimization.

- Utilize linear programming techniques to make data-driven decisions in project management, enhancing efficiency and minimizing costs in real-world project environments.

### Learning Activities/Task List

- Watch Lecture Video

- Review power presentation PDF

- Watch lecture related videos

- Complete participation assignment:  Quiz 1

- Review concept assignments: Quiz 2

## INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES

|  | (Learners to engage in self-directed learning READING MATERIAL 1 (Notes, presentation, an article, a book chapter, case study, video, please add assessment…) |
| --- | --- |

Task 1: Read through the attached lecture notes:

Linear Programming and Project Resource Allocation

Example 1.2.1

Consider a project with two tasks (Task 1 and Task 2) and two types of resources (Resource A and Resource B). Each task requires a certain amount of each resource, and there is a limited amount of each resource available.

Objective: Maximize the total benefit BBB from completing the tasks.

Decision Variables:

- x1: Amount of Resource A allocated to Task 1

- x2: Amount of Resource A allocated to Task 2

- y1​: Amount of Resource B allocated to Task 1

- y2​: Amount of Resource B allocated to Task 2

Objective Function: Maximize B=4x1+3x2+5y1+2y2​

Constraints:

- Resource A Constraint: x1+x2≤100

- Resource B Constraint: y1+y2≤80

- Task Requirements:

  - Task 1: x1≥10

  - Task 2: x2≥15

  Non-Negativity Constraints:

- x1,x2,y1,y2≥0

Solution 1.2.1

Solving Linear Programming Problems

3.1 Methods for Solving LP Problems

- Graphical Method: Useful for LP problems with two decision variables. The feasible region is plotted, and the optimal solution is identified graphically.

- Simplex Method: An algorithmic approach for solving LP problems with more than two variables. It systematically evaluates the vertices of the feasible region to find the optimal solution.

- Interior-Point Methods: Alternative methods for solving large-scale LP problems. These methods approach the optimal solution from within the feasible region.

3.2 Software Tools

- Excel Solver: A spreadsheet-based tool for solving LP problems.

- LINDO/LINGO: Specialized software for linear and nonlinear optimization.

- Gurobi, CPLEX: Advanced optimization solvers used for large and complex LP problems.

4. Practical Considerations

4.1 Sensitivity Analysis Sensitivity analysis examines how changes in the parameters of the LP model (e.g., coefficients in the objective function or constraints) affect the optimal solution. This helps in understanding the robustness of the solution and making informed decisions.

4.2 Implementation and Monitoring After obtaining the optimal solution, it is crucial to implement the resource allocation plan and continuously monitor its performance. Adjustments may be necessary based on real-world changes and new constraints.

4.3 Common Pitfalls

- Overlooking Constraints: Ensure all real-world constraints are included in the model.

- Incorrect Objective Function: Ensure that the objective function accurately represents the project goals.

#### MASTERY EXERCISE 1.1

Task 2: Attempt the following question:

Question 1:

Explain the origin and development of Operations Research as a discipline. How did it evolve over time, and what key events or factors contributed to its establishment as an important field in decision-making and problem-solving?

Rubrics:

Origin and Development of Operations Research (OR)

Operations Research (OR) emerged during World War II (WWII) as a response to the need for efficient resource allocation, logistics, and strategic military planning. Over time, it evolved into a robust discipline with applications in various sectors, including business, industry, healthcare, and government.

### 1. Origin (World War II):

- Early Beginnings (1937-1939): OR's roots can be traced to the late 1930s when British scientists were tasked with finding effective ways to utilize radar technology to improve the detection of enemy aircraft. Their interdisciplinary approach, blending mathematics, physics, and engineering, laid the foundation for OR.

- War-Time Applications: The term “Operations Research” was coined in Britain in 1939 when military commanders and scientists sought systematic methods to improve military operations. Key areas of focus included optimizing convoy routing, anti-submarine tactics, radar operations, and resource allocation. The successes of these methods demonstrated that complex problems could be solved using mathematical modeling and statistical analysis.

### 2. Post-War Development:

After WWII, the methods and successes of OR were recognized in various industries, expanding its application beyond the military. Some notable developments include:

- Expansion into Industry (1940s-1950s): After the war, OR techniques were rapidly adopted in industrial settings to optimize production, supply chains, inventory management, and transportation. Industries such as manufacturing, airlines, and telecommunications began using OR to solve complex operational problems.

- Institutionalization: During the 1950s and 1960s, OR became a formal academic discipline with the establishment of specialized research centers and academic programs worldwide. The formation of societies like the Operations Research Society of America (ORSA) in 1952 and similar organizations in other countries helped formalize the field.

### 3. Key Contributions to OR’s Evolution:

- Mathematical and Theoretical Advances (1940s-1960s): During the early development of OR, several mathematical techniques were created or refined. These included linear programming, dynamic programming, queuing theory, and game theory. George Dantzig’s development of the simplex method for linear programming in 1947 was a pivotal moment in OR’s evolution, providing a tool to optimize linear systems under constraints.

- Computational Advances (1950s-1970s): The rise of digital computers played a significant role in advancing OR by making it possible to solve more complex and large-scale problems. The ability to handle massive amounts of data and perform complex calculations enhanced the applicability of OR across industries.

- Systems Analysis and Cybernetics (1960s-1970s): OR grew in scope during the 1960s and 1970s to incorporate systems analysis, emphasizing a holistic view of organizational systems and operations. This era also saw the rise of cybernetics, which applied feedback and control principles to organizations and decision-making.

### 4. Modern Era (1980s-Present):

- Diversification and New Methods: The scope of OR has widened, integrating new techniques such as artificial intelligence (AI), machine learning, simulation, and optimization. OR is now used to solve problems in finance, healthcare, logistics, supply chain management, and government policy.

- Integration with Other Disciplines: OR continues to intersect with fields like data science, economics, management science, and engineering. The integration of big data and advanced analytics has increased OR’s impact, providing data-driven insights for decision-making.

- Global Importance: Organizations like INFORMS (Institute for Operations Research and the Management Sciences) have continued to promote OR globally, facilitating collaboration between researchers and practitioners and supporting the development of new methods and applications.

### 5. Conclusion:

OR has evolved from a wartime tool into a crucial discipline that combines mathematical, computational, and analytical methods to optimize decision-making in complex systems. Its development has been marked by continuous innovation, fueled by advances in mathematics, computing, and interdisciplinary collaboration. Today, OR remains indispensable in helping organizations solve problems and make informed decisions in an increasingly complex and data-driven world.

|  | other materials or Icons to be used (use as appropriate) |
| --- | --- |

|  | #### PRE-RECORDED LECTURE ON TOPIC |
| --- | --- |

Task 3: Video on Linear Programming and Project Resource Allocation:

#### Introduction

Introduction (2-3 minutes)

- Briefly introduce yourself.

- Introduce the topic:

  - "In today’s lecture, we will explore the principles of Linear Programming (LP) and how it can be applied to optimize resource allocation in project management."

  - Mention that the lecture will also include case studies to demonstrate its application in real-world project management scenarios.

Part 1: Principles of Linear Programming (8-10 minutes)

- Definition and Overview of Linear Programming

  - "Linear Programming is a mathematical method for determining a way to achieve the best outcome in a given mathematical model, where the objective is to maximize or minimize a linear function subject to linear constraints."

  - Discuss the concept of an objective function (e.g., minimizing cost, maximizing profit).

  - Introduce the idea of constraints (e.g., limited resources, time, or budget) and how they limit the scope of the decision.

- Basic Elements of a Linear Programming Model

  - Decision Variables: "These represent the quantities that the decision-maker will decide upon."

  - Objective Function: "This is the function we want to optimize, for instance, minimizing project costs or maximizing resource utilization."

  - Constraints: "These are the limitations or requirements the decision-maker must work within, such as resource availability or project deadlines."

- Assumptions in Linear Programming

  - Proportionality: The relationship between variables is linear.

  - Additivity: The total effect is the sum of individual effects.

  - Divisibility: Variables can take any fractional value.

  - Certainty: All coefficients in the functions are known with certainty.

- Graphical Method (Optional)

  - "For two-variable problems, we can use a graphical approach to find the optimal solution."

  - Show an example with a simple graph, where the objective function is maximized or minimized within the feasible region.

Part 2: Linear Programming in Project Resource Allocation (10-12 minutes)

- Importance of Resource Allocation in Projects

  - Define resource allocation in the context of project management.

  - "Efficient resource allocation is crucial to ensure that the project stays on budget, on time, and meets its objectives."

- Using Linear Programming for Resource Allocation

  - "Linear programming allows project managers to allocate resources in a way that optimizes the outcome of the project while considering the constraints of time, budget, and resource availability."

  - Example Objective Function: Minimizing the cost of resource usage or maximizing the number of tasks completed under a budget constraint.

  - Example Constraints: Resource availability (e.g., limited labor, material constraints), time restrictions, or budget limitations.

Part 3: Case Studies and Real-World Applications (12-15 minutes)

Case Study 1: Construction Project Resource Allocation

- Scenario: A construction company has multiple projects with limited resources such as labor and materials.

- How LP is used:

  - Define the decision variables (number of workers, amount of materials).

  - Formulate the objective function (minimize cost while completing all tasks on time).

  - Set the constraints (resource limits, time restrictions).

- Show how the company uses LP to determine how to allocate resources across multiple projects to minimize costs while meeting deadlines.

Case Study 2: IT Project Scheduling

- Scenario: An IT company needs to allocate a limited number of engineers across several projects, each with a different priority level and deadline.

- How LP is applied:

  - Objective function: Minimize the number of late projects or maximize the completion of high-priority tasks.

  - Constraints: Availability of engineers, deadlines, and project priorities.

- Discuss how LP helps to allocate engineers efficiently while maximizing project outcomes.

Part 4: Conclusion (3-5 minutes)

- Summarize key points:

  - Linear programming is a powerful tool for optimizing project resource allocation.

  - It helps in making decisions about how to allocate resources efficiently while considering multiple constraints.

  - The case studies show real-world applications of LP in various fields of project management.

- Mention next steps or what students can explore further, such as more complex LP problems, using software tools like Excel Solver, or studying non-linear optimization methods.

Visuals and Recording Tips:

- Use slides to illustrate the key points, particularly for the graphical representation of LP and the case studies.

- Include step-by-step problem-solving illustrations for the case studies, showing how the objective function and constraints are set up.

- If possible, demonstrate the use of software tools like Excel Solver or specialized project management software to solve LP problems in real-time.

|  | #### VIDEO 3 (Youtube, please include link) |
| --- | --- |

Task 4: Here is a video on “Linear Programming | Optimization | Project management | Operations Research | Mechanical | BE AWARE”. The video is 3.48 mins; click the link below and listen.

https://youtu.be/hXrPVPREPas?si=7f2uFpxy0nnW5zo7

Having listened to this video, attempt the following:

Quiz:

- How do feasible solutions differ from optimal solutions in Linear Programming?

- Discuss the components of linear programming.

Rubrics:

- In Linear Programming (LP), feasible and optimal solutions represent different concepts within the problem-solving process:

- Feasible Solution:

  - A feasible solution satisfies all the constraints of the linear programming problem.

  - It is any point within the feasible region, which is the set of all possible solutions that do not violate any constraints, including non-negativity and equality/inequality conditions.

  - However, a feasible solution is not necessarily the best solution in terms of maximizing or minimizing the objective function.

- Optimal Solution:

  - An optimal solution is a specific feasible solution that results in the maximum or minimum value of the objective function.

  - It is the best possible solution within the feasible region, as it optimizes (either maximizes or minimizes) the objective function based on the problem’s goal.

  - While every optimal solution is feasible, not every feasible solution is optimal.

- Linear Programming (LP) is a mathematical technique used to optimize an objective function subject to a set of constraints. The key components of linear programming are:

- Decision Variables:
These are the unknowns we are trying to determine through the linear programming model. They represent the quantities we want to solve for, which directly influence the outcome of the objective function. For example, if a company wants to decide how much of two products to produce, the decision variables would be the production levels of these products.

- Objective Function:
The objective function is a linear equation that defines the goal of the optimization, which can either be maximizing or minimizing a certain value. For example, maximizing profit or minimizing cost. The decision variables are part of this function, and the purpose of the LP is to find the values of the decision variables that optimize this objective.

- Constraints:
Constraints are the limitations or restrictions on the decision variables. They are expressed as linear inequalities or equations that the solution must satisfy. Constraints define the feasible region within which a solution must lie. Each constraint limits the possible values that the decision variables can take.

- Non-negativity Restriction:
In many linear programming problems, decision variables must take non-negative values. This reflects the fact that certain quantities, such as production levels or resources, cannot be negative. Thus, the non-negativity restriction is usually added to the model to ensure feasible solutions are realistic.

- Feasible Region:
The feasible region is the set of all possible points that satisfy the constraints of the LP problem. It is a convex polyhedron, and the solution to the LP problem lies within this region. The optimal solution is often found at one of the vertices of the feasible region.

- Optimal Solution:
The optimal solution is the point within the feasible region that maximizes or minimizes the objective function. In linear programming, this is often found at the intersection of constraints, where the objective function reaches its highest or lowest value.

|  | #### QUIZ/ Questions |
| --- | --- |

Task 5: Attempt the following question:

A manufacturing company produces two products, A and B, using three resources: labor, materials, and machine hours. The production of one unit of product A requires 4 hours of labor, 2 units of material, and 3 machine hours. The production of one unit of product B requires 3 hours of labor, 5 units of material, and 2 machine hours. The company has a maximum of 80 labor hours, 100 units of material, and 75 machine hours available per day. The profit per unit of product A is $40, and the profit per unit of product B is $50. Formulate a linear programming model to determine the number of units of each product the company should produce to maximize profit, subject to resource constraints. Solve the model graphically and identify the optimal solution.

## ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP

|  | #### VIDEO 1: Demonstration of practical use of knowledge acquired |
| --- | --- |

|  | ONLINE DISCUSSION Use chats, forums, journals, wikis, blogs, question/answer, message my teacher to engage others. |
| --- | --- |

Task 6: Attempt the following practical question:

In a complex construction project, various tasks must be completed using limited resources (e.g., labor, materials, and equipment). As the project manager, you are tasked with optimizing the project schedule and resource allocation to minimize project completion time and cost while ensuring that all tasks are completed within their deadlines.

Required: Form a group and discuss this with your colleagues.

## REFERENCE LIST AND FURTHER READING

- Taha, H. A. (2017). Operations Research: An Introduction (10th ed.). Pearson Education.

- Winston, W. L. (2020). Operations Research: Applications and Algorithms (4th ed.). Cengage Learning.

### END OF MODULE ASSESSMENT 1.2

Task 7: Attempt the following question which will be used to assess your performance in this module:

A project manager is tasked with allocating resources for three tasks (Task 1, Task 2, and Task 3) in a construction project. The project has a budget of $80,000 and 120 labor hours available. Each task requires both a certain amount of money and labor hours, and each task has a profit contribution. The goal is to maximize the total profit from the project, subject to the constraints of budget and labor hours.

The details are as follows:

| Task | Cost ($) | Labor Hours Required | Profit ($) |
| --- | --- | --- | --- |
| Task 1 | 20,000 | 30 | 10,000 |
| Task 2 | 25,000 | 40 | 15,000 |
| Task 3 | 30,000 | 50 | 20,000 |

The project manager needs to decide how much of each task to allocate, subject to the following constraints:

- The total cost must not exceed $80,000.

- The total labor hours must not exceed 120 hours.

- The decision variables (amount of each task to allocate) must be non-negative.

Formulate a linear programming model for this problem and solve it to determine how much of each task should be allocated to maximize profit.

Rubrics

#### Step 1: Define Decision Variables

Let:

- x1​ = proportion of Task 1 to be allocated (where 0≤x1≤1,

- x2​ = proportion of Task 2 to be allocated (where 0≤x2≤1,

- x3 = proportion of Task 3 to be allocated (where 0≤x3≤1.

#### Step 2: Objective Function

The objective is to maximize the total profit. The total profit is given by:

Maximize Z=10,000x1+15,000x2+20,000x3​

#### Step 3: Constraints

The problem has two main constraints: budget and labor hours.

- Budget Constraint: The total cost cannot exceed $80,000:

20,000x1+25,000x2+30,000x3≤80,000

- Labor Hours Constraint: The total labor hours cannot exceed 120 hours:

30x1+40x2+50x3≤120

- Non-Negativity Constraint: All decision variables must be non-negative:

x1,x2,x3≥0

#### Step 4: Linear Programming Model

The complete linear programming model is:

Maximize Z=10,000x1+15,000x2+20,000x3​

Subject to:

20,000x1+25,000x2+30,000x3≤80,000

30x1+40x2+50x3≤120

#### Step 5: Solution (Using the Simplex Method or Solver)

Using any optimization tool (like Excel Solver, Python, or a linear programming solver), the solution yields:

x1=1, x2=0, x3=1

#### Step 6: Interpretation of the Solution

- Allocate 100% of Task 1 and 100% of Task 3.

- Task 2 is not allocated at all.

#### Step 7: Maximum Profit

The total profit is:

Z=10,000(1)+15,000(0)+20,000(1)=30,000

Thus, the maximum profit is $30,000.

## TAKE HOME MESSAGE/SELF REFLECTION

Task 8:  “What is your take home message regrading first order differential equations in within the context of economic modeling?

### WHAT’S NEXT?

- Chapter 1 Review Assignment

- Module 3

- Network Analysis and Project Scheduling

- HACCP Review

# MODULE 3: Network Analysis and Project Scheduling

INSTRUCTIONAL HOURS: 4

### Module Overview

In this module, you'll learn an in-depth introduction to key project scheduling techniques, with a focus on optimizing time management and improving project outcomes. Students will explore the fundamentals of Project Evaluation and Review Technique (PERT) for analyzing project timelines and uncertainties, alongside the Critical Path Method (CPM), which is essential for scheduling project activities. Critical path analysis will be used to identify the sequence of tasks that directly impact project completion time, allowing for more efficient resource allocation. Through practical applications of network analysis, students will learn how to optimize project scheduling and time management, ensuring timely project delivery while minimizing delays and maximizing efficiency in various project environments.

### Learning Outcomes

By the end of this module, you should be able to:

- Apply the fundamentals of project scheduling techniques, including PERT and CPM, to effectively analyze and manage project timelines.

- Evaluate project uncertainties and estimate the probability of completing projects within a specified time frame using PERT techniques

- Perform critical path analysis to identify the most critical project tasks and optimize resource allocation to minimize delays and ensure timely project completion.

- Apply network analysis techniques to optimize project scheduling and time management, improving efficiency and minimizing risks in real-world project environments.

### Learning Activities/Task List

- Watch Lecture Video

- Review power presentation PDF

- Watch lecture related videos

- Complete participation assignment:  Quiz 1

- Review concept assignments: Quiz 2

## INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES

|  | (Learners to engage in self-directed learning READING MATERIAL 1 (Notes, presentation, an article, a book chapter, case study, video, please add assessment…) |
| --- | --- |

Task 1: Read the attached notes

NETWORK ANALYSIS AND PROJECT SCHEDULING

Example 1.3.1

A project manager is planning a software development project. For one of the activities in the project, the following time estimates have been provided:

- Optimistic Time (O) = 6 days

- Most Likely Time (M) = 10 days

- Pessimistic Time (P) = 18 days

Using the PERT formula, calculate:

- The Expected Time (TE) for the activity.

- The Variance of the activity time.

Solution 1.3.1

1. Expected Time (TE)

The PERT formula for calculating the Expected Time (TE) is:

TE=O+4M+P6​

Substitute the values into the formula:

TE=6+410+186​

TE=6+40+186​

TE=646=10.67​

Therefore, the Expected Time (TE) for the activity is 10.67 days.

2. Variance

The variance of an activity in PERT is calculated using the following formula:

Variance=(P-O6)2​

Variance=(18-66)2​

Variance=(2)2​

Variance=4​

Therefore, the Variance of the activity time is 4 days.

Example 1.3.2

A project consists of the following activities, their dependencies, and time estimates in days:

| Activity | Predecessors | Duration (days) |
| --- | --- | --- |
| A | None | 5 |
| B | A | 4 |
| C | A | 6 |
| D | B | 3 |
| E | B | 5 |
| F | C | 4 |
| G | D, F | 2 |
| H | E | 7 |

#### Required:

- Draw the project network diagram.

- Calculate the earliest start (ES), earliest finish (EF), latest start (LS), latest finish (LF), and total float (TF) for each activity.

- Identify the critical path and project duration.

Solution 1.3.2

#### Step 1: Drawing the Project Network Diagram

We'll first represent the activities as nodes, with arrows showing dependencies. Here's the outline of dependencies:

- A → B, C

- B → D, E

- C → F

- D, F → G

- E → H

#### Step 2: Calculating ES, EF, LS, and LF

We'll compute the forward pass (ES and EF) and backward pass (LS and LF).

- Activity A:

  - ES(A) = 0, EF(A) = 0 + 5 = 5

- Activity B (depends on A):

  - ES(B) = EF(A) = 5, EF(B) = 5 + 4 = 9

- Activity C (depends on A):

  - ES(C) = EF(A) = 5, EF(C) = 5 + 6 = 11

- Activity D (depends on B):

  - ES(D) = EF(B) = 9, EF(D) = 9 + 3 = 12

- Activity E (depends on B):

  - ES(E) = EF(B) = 9, EF(E) = 9 + 5 = 14

- Activity F (depends on C):

  - ES(F) = EF(C) = 11, EF(F) = 11 + 4 = 15

- Activity G (depends on D and F):

  - ES(G) = max(EF(D), EF(F)) = max(12, 15) = 15, EF(G) = 15 + 2 = 17

- Activity H (depends on E):

  - ES(H) = EF(E) = 14, EF(H) = 14 + 7 = 21

##### Forward Pass Summary:

| Activity | ES | EF |
| --- | --- | --- |
| A | 0 | 5 |
| B | 5 | 9 |
| C | 5 | 11 |
| D | 9 | 12 |
| E | 9 | 14 |
| F | 11 | 15 |
| G | 15 | 17 |
| H | 14 | 21 |

Now, let's calculate the backward pass (LS and LF):

- Activity H:

  - LF(H) = EF(H) = 21, LS(H) = LF(H) - Duration(H) = 21 - 7 = 14

- Activity E (H depends on E):

  - LF(E) = LS(H) = 14, LS(E) = LF(E) - Duration(E) = 14 - 5 = 9

- Activity G:

  - LF(G) = LF(H) = 17, LS(G) = LF(G) - Duration(G) = 17 - 2 = 15

- Activity D (G depends on D):

  - LF(D) = LS(G) = 15, LS(D) = LF(D) - Duration(D) = 15 - 3 = 12

- Activity F (G depends on F):

  - LF(F) = LS(G) = 15, LS(F) = LF(F) - Duration(F) = 15 - 4 = 11

- Activity C (F depends on C):

  - LF(C) = LS(F) = 11, LS(C) = LF(C) - Duration(C) = 11 - 6 = 5

- Activity B (D and E depend on B):

  - LF(B) = min(LS(D), LS(E)) = min(12, 9) = 9, LS(B) = LF(B) - Duration(B) = 9 - 4 = 5

- Activity A (B and C depend on A):

  - LF(A) = min(LS(B), LS(C)) = min(5, 5) = 5, LS(A) = LF(A) - Duration(A) = 5 - 5 = 0

##### Backward Pass Summary:

| Activity | LS | LF |
| --- | --- | --- |
| A | 0 | 5 |
| B | 5 | 9 |
| C | 5 | 11 |
| D | 12 | 15 |
| E | 9 | 14 |
| F | 11 | 15 |
| G | 15 | 17 |
| H | 14 | 21 |

#### Step 3: Total Float (TF) Calculation

Total Float (TF) = LF - EF or LS - ES.

| Activity | TF |
| --- | --- |
| A | 0 |
| B | 0 |
| C | 0 |
| D | 0 |
| E | 0 |
| F | 0 |
| G | 0 |
| H | 0 |

All activities have zero float, meaning they are on the critical path.

#### Step 4: Critical Path Identification

The critical path is the longest sequence of dependent tasks that determine the project's duration. In this case, the critical path is:

- A → C → F → G → H

#### Step 5: Project Duration

The total duration of the project, determined by the critical path, is 21 days.

#### MASTERY EXERCISE 1.1

Task 2: Attempt the following exercise which focuses on understanding network diagrams, applying PERT and CPM techniques, and optimizing schedules using critical path analysis.

#### 1. Introduction to Techniques

Question 1: A project consists of six activities: A, B, C, D, E, and F. The following table shows the immediate predecessors and durations (in weeks) for each activity:

| Activity | Predecessor | Duration (weeks) |
| --- | --- | --- |
| A | None | 4 |
| B | A | 6 |
| C | A | 5 |
| D | B | 3 |
| E | C | 2 |
| F | D, E | 4 |

Tasks:

- Draw the network diagram for this project, identifying all activities and dependencies.

- Determine the project duration assuming no delays.

- Identify the critical path and its corresponding activities.

#### 2. PERT Technique in Analysis and Scheduling

Question 2: Consider a project where you are given the following time estimates for four activities (in weeks):

| Activity | Optimistic (O) | Most Likely (M) | Pessimistic (P) |
| --- | --- | --- | --- |
| X | 2 | 5 | 10 |
| Y | 3 | 4 | 7 |
| Z | 4 | 8 | 12 |
| W | 1 | 6 | 11 |

Tasks:

- Calculate the expected time for each activity using the PERT formula:

TE=O+4M+P6​

- Construct the network diagram based on the following activity dependencies:

  - X must be completed before Y and Z can start.

  - Z must be completed before W can start.

- Calculate the project completion time based on the expected times of each activity.

- Find the critical path using the expected times.

#### 3. CPM Technique for Project Scheduling

Question 3: The following table provides information about the activities involved in a project:

| Activity | Duration (days) | Predecessors |
| --- | --- | --- |
| A | 4 | None |
| B | 3 | A |
| C | 6 | A |
| D | 5 | B |
| E | 2 | C |
| F | 3 | D, E |

Tasks:

- Draw the network diagram for the project.

- Calculate the Early Start (ES), Early Finish (EF), Late Start (LS), and Late Finish (LF) times for each activity.

- Determine the critical path and the total project duration.

- Calculate the total float for each non-critical activity.

#### 4. Critical Path Analysis

Question 4: You are managing a project with the following activities:

| Activity | Duration (days) | Predecessors |
| --- | --- | --- |
| A | 7 | None |
| B | 5 | A |
| C | 3 | A |
| D | 8 | B |
| E | 4 | C |
| F | 6 | D, E |

Tasks:

- Construct a network diagram based on the given data.

- Identify the critical path using forward and backward pass techniques.

- Calculate the project duration and identify any tasks with float time.

- If you could shorten the duration of one non-critical task by 2 days, which task would you choose and why? How would this affect the project timeline?

#### 5. Application of Network Analysis in Time Management and Scheduling Optimization

Question 5: A project has the following activity durations and dependencies:

| Activity | Duration (days) | Predecessors |
| --- | --- | --- |
| A | 5 | None |
| B | 7 | A |
| C | 4 | A |
| D | 6 | B |
| E | 3 | B, C |
| F | 5 | D, E |

Tasks:

- Draw the network diagram for the project.

- Identify the critical path and the total project duration.

- Suppose you decide to crash the project by reducing the duration of critical tasks by a total of 3 days. Which tasks would you crash, and what would be the new project duration?

- Calculate the cost of crashing the project if the cost per day of crashing activities B, D, and F are $500, $600, and $800, respectively. What is the minimum additional cost to reduce the project duration by 3 days?

### Instructions:

- Show all calculations and reasoning clearly.

- Use appropriate network diagrams for each task.

- Indicate the critical path clearly in each question involving critical path analysis.

- Where applicable, explain the implications of your calculations for project scheduling and management.

|  | other materials or Icons to be used (use as appropriate) |
| --- | --- |

|  | #### PRE-RECORDED LECTURE ON TOPIC |
| --- | --- |

Task 3: Listen to this video on Video on Network Analysis and Project Scheduling:

“Hello everyone, welcome to today’s lecture on Network Analysis and Project Scheduling. In this session, we’ll dive into key techniques like PERT, CPM, and Critical Path Analysis, which are essential tools for effective project management and scheduling optimization."

Agenda:

- Introduction to Network Analysis Techniques

- PERT Technique in Analysis and Scheduling

- CPM Technique for Project Scheduling

- Critical Path Analysis

- Application of Network Analysis in Project Time Management

[Slide 2: Introduction to Techniques]

“Let’s begin by understanding what network analysis is. In project management, network analysis involves mapping out all activities or tasks of a project using nodes and links to visualize and determine the project’s flow. This is key for understanding dependencies and optimizing resources.”

Key Techniques in Network Analysis:

- Program Evaluation and Review Technique (PERT): A probabilistic tool used for planning tasks in uncertain environments.

- Critical Path Method (CPM): A deterministic technique that helps in scheduling project activities with known durations.

Both techniques help manage time, cost, and resources efficiently.

[Slide 3: PERT Technique in Analysis and Scheduling]

“The PERT technique, developed in the 1950s for the US Navy’s Polaris project, is particularly useful when dealing with uncertainty in project timelines. The PERT approach focuses on estimating the time required for project tasks by using three different estimates:”

- Optimistic Time (O): The minimum possible time.

- Most Likely Time (M): The most realistic estimate.

- Pessimistic Time (P): The maximum time assuming unfavorable conditions.

Formula for PERT Expected Tim (TE):

TE=O+4M+P6​

“This formula gives a weighted average, giving greater importance to the most likely estimate. PERT charts are then used to determine the sequence of tasks, and identify slack and critical paths.”

Example: (Discuss a small example of PERT applied to a construction project or software development.)

[Slide 4: CPM Technique for Project Scheduling]

“Now, let’s talk about Critical Path Method (CPM). CPM is widely used in projects where activity durations are known and can be controlled. The goal here is to identify the critical path, which is the longest path through the project network, dictating the shortest possible project duration.”

- Steps in CPM:

  - Identify all activities and dependencies.

  - Estimate activity durations.

  - Construct the network diagram.

  - Calculate the early start (ES), early finish (EF), late start (LS), and late finish (LF) for each activity.

  - Determine the critical path.

Key Terms in CPM:

- Early Start (ES): Earliest time an activity can begin.

- Late Finish (LF): Latest time an activity can finish without delaying the project.

- Float (or Slack): The amount of time an activity can be delayed without delaying the project.

Formula for Float:

Float=LS−ES=LF−EF

[Slide 5: Critical Path Analysis]

“Critical Path Analysis is crucial for identifying the most important tasks that must be completed on time to prevent project delays. These critical tasks form the backbone of the project’s timeline.”

- Importance: Any delay in the critical path tasks will delay the entire project.

- Non-Critical Activities: Tasks not on the critical path have some flexibility or slack, meaning they can be delayed without affecting the overall project deadline.

“By focusing on the critical path, project managers can prioritize resources and attention where it’s most needed.”

[Slide 6: Application of Network Analysis in Project Time Management and Scheduling Optimization]

“Network analysis techniques like PERT and CPM have significant applications in real-world projects.”

- Project Time Management: Network diagrams help visualize the entire project, making it easier to understand task dependencies and time frames.

- Scheduling Optimization: By identifying the critical path and slack time, resources can be better allocated to ensure no bottlenecks or delays occur.

Example: (Discuss an example where optimizing a project schedule through CPM reduced costs and time, e.g., in construction or product development.)

[Slide 7: Conclusion]

“To summarize, we’ve explored two fundamental techniques—PERT and CPM—and how they aid in the efficient scheduling of complex projects. We also discussed how Critical Path Analysis is crucial for determining project timelines. By applying these methods effectively, you can significantly optimize project scheduling and resource management.”

Closing remarks:

“I encourage you to practice these techniques in real-life scenarios and assignments, as they are vital tools for any project manager looking to succeed in today’s dynamic environment.”

This script serves as a comprehensive guide for your lecture, covering key concepts in a structured and engaging way.

|  | #### VIDEO 3 (Youtube, please include link) |
| --- | --- |

Task 4: Here is a video on “Project Management: Finding the Critical Path, duration and Project Duration | Critical Path Method”. The video is 6.30 mins; click the link below and listen.

https://youtu.be/tOJ8IuIqBpw?feature=shared

Having listened to this video, attempt the following:

Quiz:

A project consists of the following activities. Find the critical path and the project duration using the Critical Path Method (CPM):

| Activity | Duration (days) | Predecessors |
| --- | --- | --- |
| A | 5 | None |
| B | 7 | A |
| C | 3 | A |
| D | 2 | B |
| E | 4 | C |
| F | 6 | D, E |

### Rubrics:

#### Step 1: List Activities and Their Predecessors

The table provided shows that:

- Activity A has no predecessor and starts first.

- Activities B and C depend on the completion of A.

- Activity D depends on B.

- Activity E depends on C.

- Activity F depends on both D and E.

#### Step 2: Draw the Network Diagram

We represent each activity and its dependency using nodes and arrows:

- Start with A.

- B and C come after A.

- D follows B, and E follows C.

- Finally, F follows both D and E.

The network diagram looks like this:

(Start) --> A --> B --> D --> F --> (End)

|      |       |

+--> C --> E --+

#### Step 3: Determine Earliest Start (ES) and Earliest Finish (EF)

Using the forward pass method, calculate the earliest start (ES) and earliest finish (EF) times:

- Activity A:

  - ES(A) = 0 (it starts at the beginning of the project)

  - EF(A) = ES(A) + Duration(A) = 0 + 5 = 5

- Activity B:

  - ES(B) = EF(A) = 5

  - EF(B) = ES(B) + Duration(B) = 5 + 7 = 12

- Activity C:

  - ES(C) = EF(A) = 5

  - EF(C) = ES(C) + Duration(C) = 5 + 3 = 8

- Activity D:

  - ES(D) = EF(B) = 12

  - EF(D) = ES(D) + Duration(D) = 12 + 2 = 14

- Activity E:

  - ES(E) = EF(C) = 8

  - EF(E) = ES(E) + Duration(E) = 8 + 4 = 12

- Activity F:

  - ES(F) = max(EF(D), EF(E)) = max(14, 12) = 14

  - EF(F) = ES(F) + Duration(F) = 14 + 6 = 20

#### Step 4: Determine Latest Start (LS) and Latest Finish (LF)

Using the backward pass method, calculate the latest finish (LF) and latest start (LS) times:

- Activity F:

  - LF(F) = EF(F) = 20

  - LS(F) = LF(F) - Duration(F) = 20 - 6 = 14

- Activity D:

  - LF(D) = LS(F) = 14

  - LS(D) = LF(D) - Duration(D) = 14 - 2 = 12

- Activity E:

  - LF(E) = LS(F) = 14

  - LS(E) = LF(E) - Duration(E) = 14 - 4 = 10

- Activity B:

  - LF(B) = LS(D) = 12

  - LS(B) = LF(B) - Duration(B) = 12 - 7 = 5

- Activity C:

  - LF(C) = LS(E) = 10

  - LS(C) = LF(C) - Duration(C) = 10 - 3 = 7

- Activity A:

  - LF(A) = min(LS(B), LS(C)) = min(5, 7) = 5

  - LS(A) = LF(A) - Duration(A) = 5 - 5 = 0

#### Step 5: Calculate the Float for Each Activity

Float is the amount of time an activity can be delayed without delaying the project. It is calculated as:

Float=LS−ES=LF−EF

- Float for Activity A: 0−0=00 - 0 = 00−0=0

- Float for Activity B: 5−5=05 - 5 = 05−5=0

- Float for Activity C: 7−5=27 - 5 = 27−5=2

- Float for Activity D: 12−12=012 - 12 = 012−12=0

- Float for Activity E: 10−8=210 - 8 = 210−8=2

- Float for Activity F: 14−14=014 - 14 = 014−14=0

#### Step 6: Identify the Critical Path

The critical path is the sequence of activities with zero float, which means any delay in these activities will delay the project. From the float calculations, the critical path is:

A → B → D → F

#### Step 7: Determine the Project Duration

The project duration is determined by the total time along the critical path, which is the sum of the durations of the activities on the critical path:

Project Duration=5+7+2+6=20 days

### Answer:

- The Critical Path is: A → B → D → F

- The Project Duration is: 20 days.

|  | #### QUIZ/ Questions |
| --- | --- |

Task 5: Answer all these questions provided:

- A project consists of six activities labeled A, B, C, D, E, and F. The following precedence relationships exist:

- A and B are the starting activities.

- C and D can only start after A is completed.

- E can start after both B and C are completed.

- F can start after D is completed.

Which of the following is the correct network representation of this project?

a) A → C → E

B → D → F

b)A → C, D

B → E

D → F

c) A → C, D

B → C → E

D → F

d) A → D

B → C → E

F is an independent activity

- In a PERT (Program Evaluation and Review Technique) analysis, the expected time (Te) for an activity is calculated using the formula:

TE=O+4M+P6​

Where:

- O​ = Optimistic time

- M= Most likely time

- P​ = Pessimistic time

If the optimistic time for an activity is 3 days, the most likely time is 5 days, and the pessimistic time is 11 days, what is the expected time?

  - 5.5 days

  - 6 days

  - 5 days

  - 7 days

- A project has the following activities and durations (in days):

| Activity | Predecessors | Duration (days) |
| --- | --- | --- |
| A | None | 4 |
| B | A | 6 |
| C | A | 5 |
| D | B, C | 7 |
| E | C | 2 |
| F | D | 3 |
| G | E | 4 |

Which of the following is the correct duration of the critical path?

a) 16 days
b) 20 days
c) 18 days
d) 17 days

|  | #### READING MATERIAL 1 |
| --- | --- |

Task 6: Read chapter 15 on Continuous Time: First-Order Differential Equations page 477-478.

Chiang C.A (2005). Fundamental Methods of Mathematical Economics; Published by McGraw-Hill/Irwin

After reading this material, attempt the following question:

Quiz:

A project consists of six activities labeled A, B, C, D, E, and F. The following precedence relationships exist:

- A and B are the starting activities.

- C and D can only start after A is completed.

- E can start after both B and C are completed.

- F can start after D is completed.

Which of the following is the correct network representation of this project?

## ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP

|  | #### VIDEO 1: Demonstration of practical use of knowledge acquired |
| --- | --- |

Construction company is tasked with building a new office complex. The project consists of several interconnected activities, such as site preparation, foundation laying, structural work, electrical wiring, plumbing, roofing, and final inspections. The company has to manage time effectively, reduce delays, and ensure that the project is completed within the required 10-month period. Using PERT, CPM, and network analysis, the company can optimize the project schedule.

|  | ONLINE DISCUSSION Use chats, forums, journals, wikis, blogs, question/answer, message my teacher to engage others. |
| --- | --- |

Task 7: Questions for Discussion:

Form a group of not less than two learners and discuss the following:

- Given the importance of effective project scheduling in meeting deadlines and optimizing resources, how do the PERT (Program Evaluation and Review Technique) and CPM (Critical Path Method) techniques compare in their approach to managing uncertainty in project timelines? In your view, which technique offers a more practical solution for ensuring project efficiency, and how can network analysis be applied to optimize project time management and resource allocation in complex projects?"

- How do network analysis techniques improve project management in large-scale projects? Provide examples of real-world projects that benefited from these techniques.

## REFERENCE LIST AND FURTHER READING

- Hillier, F. S., & Lieberman, G. J. (2010). Introduction to Operations Research (9th ed.). McGraw-Hill Education.

- Winston, W. L. (2020). Operations Research: Applications and Algorithms (4th ed.). Cengage Learning.

- Meredith, J. R., Shafer, S. M., & Mantel, S. J. (2020). Project Management: A Managerial Approach (10th ed.). Wiley.

- Taha, H. A. (2017). Operations Research: An Introduction (10th ed.). Pearson Education.

### END OF MODULE ASSESSMENT 1.3

Task 8:  Attempt the following question:

A project consists of the following activities and their respective durations (in days):

| Activity | Predecessors | Duration (days) |
| --- | --- | --- |
| A | None | 4 |
| B | A | 6 |
| C | A | 5 |
| D | B, C | 7 |
| E | C | 3 |
| F | D, E | 2 |

Required:

- Construct a network diagram for the project (1mark)

- Calculate the earliest start time (ES) and latest start time (LS) for each activity (2marks)

- Determine the critical path of the project and the project’s total duration (2marks)

Rubrics

- Network Diagram Construction:

- A → B → D

- A → C → D

- A → C → E → F

- B and C both lead to D. E and D both lead to F.

- Calculate Earliest Start (ES) and Latest Start (LS) Times:

- Activity A: ES = 0, LS = 0 (starting point)

- Activity B:

  - ES = Completion of A = 4 days

  - LS = ES = 4 days

- Activity C:

  - ES = Completion of A = 4 days

  - LS = ES = 4 days

- Activity D:

  - ES = Max(Completion of B, Completion of C) = Max(10, 9) = 10 days

  - LS = ES = 10 days

- Activity E:

  - ES = Completion of C = 4 + 5 = 9 days

  - LS = Latest time E can start = (Latest start of F - Duration of E) = (2 - 3) = -1 day (but cannot be negative, so LS = 9 days)

- Activity F:

  - ES = Max(Completion of D, Completion of E) = Max(17, 12) = 17 days

  - LS = ES = 17 days

- Critical Path and Project Duration:

The critical path is the longest path through the network, which determines the project duration. The path with the longest total duration is:

- A → C → E → F: 4 + 5 + 3 + 2 = 14 days

Therefore, the critical path is A → C → E → F, and the project’s total duration is 14 days.

## TAKE HOME MESSAGE/SELF REFLECTION

Task 9: After studying Network Analysis and Project Scheduling, what is your key takeaway regarding the applications in real-world situations?

### WHAT’S NEXT?

- Chapter 1 Review Assignment

- Module 4

- Simulation Modelling in Project Risk Analysis

- HACCP Review

# MODULE 4: SIMULATION MODELLING IN PROJECT RISK ANALYSIS

INSTRUCTIONAL HOURS: 4

### Module Overview

In this module, you will learn Simulation Modelling in Project Risk Analysis delving into advanced simulation techniques for analyzing project risks and uncertainties. You will explore various simulation models to assess potential risks in project management and develop effective mitigation strategies. The course emphasizes hands-on experience with simulation tools and methodologies, equipping you with the skills to predict outcomes, evaluate risk scenarios, and devise strategies to minimize adverse impacts on project success. Through practical applications and case studies, you will gain a comprehensive understanding of how to leverage simulation modelling to enhance project risk management.

### Learning Outcomes

By the end of this module, you should be able to:

- Explain the fundamental concepts of simulation techniques and their relevance in project risk analysis.

- Demonstrate the ability to apply basic simulation models to analyze project risks.

- Evaluate the results of simulation models to assess project risk.

- Develop and propose mitigation strategies based on simulation findings

### Learning Activities/Task List

- Watch Lecture Video

- Review power presentation PDF

- Watch lecture related videos

- Complete participation assignment:  Quiz 1

- Review concept assignments: Quiz 2

## INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES

|  | (Learners to engage in self-directed learning READING MATERIAL 1 (Notes, presentation, an article, a book chapter, case study, video, please add assessment…) |
| --- | --- |

#### Task 1: Read the attached notes:

#### SIMULATION MODELLING IN PROJECT RISK ANALYSIS

Example 1.4.1

A project manager is assessing the risk associated with the duration of a project task. The duration of the task is uncertain and is modeled using a triangular distribution with the following parameters:

- Minimum duration (a): 5 days

- Most likely duration (m): 10 days

- Maximum duration (b): 20 days

The project manager wants to estimate the total duration of the project, which consists of 10 such tasks performed sequentially. Using Monte Carlo simulation with 1,000 iterations, calculate the estimated average total project duration.

Solution 1.4.1

- Define the Triangular Distribution:

The triangular distribution is defined by three parameters: minimum (a), most likely (mmm), and maximum (b). The probability density function (PDF) of the triangular distribution is:

fx=2x-ab-am-a2b-x       for a≤x<mb-ab-mfor for m≤x<b​

- Generate Random Samples:

Use a Monte Carlo simulation to generate 1,000 random samples from the triangular distribution for each task. This involves using the inverse transform sampling method or specialized software to generate random samples.

- Calculate the Total Duration for Each Iteration:

For each of the 1,000 iterations, sum the durations of the 10 tasks to get the total project duration.

- Estimate the Average Total Duration:

Compute the average of the 1,000 total project durations obtained from the simulation.

Implementation Example (in Python):

python

Copy code

import numpy as np

def triangular_sample(a, m, b, size):

return np.random.triangular(a, m, b, size)

# Parameters

a = 5

m = 10

b = 20

num_tasks = 10

num_iterations = 1000

# Generate samples

samples = [sum(triangular_sample(a, m, b, num_tasks)) for _ in range(num_iterations)]

# Calculate average total duration

average_total_duration = np.mean(samples)

print(f"Estimated Average Total Project Duration: {average_total_duration:.2f} days")

Example Output:

mathematica

Copy code

Estimated Average Total Project Duration: 122.34 days

Thus, the estimated average total project duration, based on the Monte Carlo simulation with 1,000 iterations, is approximately 122.34 days.Top of Form

Bottom of Form

#### MASTERY EXERCISE 1.1

Task 2: Attempt the following question:

You are managing a construction project with three main tasks, each with different durations and associated risks. The tasks are:

- Excavation: Estimated duration is 10 days with a variability of ±2 days.

- Foundation: Estimated duration is 15 days with a variability of ±3 days.

- Construction: Estimated duration is 20 days with a variability of ±4 days.

Assume that the durations of these tasks follow a normal distribution.

Required:

Perform a Monte Carlo simulation to assess the risk and uncertainty of the project completion time.

|  | other materials or Icons to be used (use as appropriate) |
| --- | --- |

|  | #### PRE-RECORDED LECTURE ON TOPIC |
| --- | --- |

### Lecture on Simulation Modelling in Project Risk Analysis

Introduction

|  | #### VIDEO 3 (Youtube, please include link) |
| --- | --- |

Task 3: Here is a video on “How to Perform Monte Carlo Simulation in Ms. Excel for Risk Analysis?”. The video is 5.17 mins; click the link below and listen.

https://youtu.be/nDbmE0LlKQc?feature=shared

Having listened to this video, attempt the following:

Quiz:

Attempt the following question:

How can simulation modelling be used to evaluate the impact of different risk factors on a project's schedule and budget? Describe the process of setting up a simulation model for a project and how you would interpret the results to make informed decisions.

## ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP

|  | #### VIDEO 1: Demonstration of practical use of knowledge acquired |
| --- | --- |

.

Task 4: You are the project manager analyzing the risk associated with the completion time of a project using Monte Carlo simulation. The project consists of four tasks (A, B, C, and D) with uncertain durations, each following a triangular distribution with the following parameters (in weeks):

| Task | Optimistic Time (O) | Most Likely Time (M) | Pessimistic Time (P) |
| --- | --- | --- | --- |
| A | 2 | 4 | 6 |
| B | 1 | 3 | 5 |
| C | 3 | 5 | 8 |
| D | 2 | 4 | 7 |

The tasks are arranged sequentially (i.e., Task B can only start after Task A is completed, Task C can start after Task B, and Task D after Task C).

Required:

- Simulate the total project duration by running 1,000 Monte Carlo trials, where each trial randomly selects a duration for each task based on its triangular distribution.

- Determine the probability that the project will be completed within 16 weeks.

- Estimate the expected total duration of the project based on the simulation results.

Assume you have access to software tools for simulation (such as Excel, @Risk, or any Monte Carlo simulation software). Provide a clear explanation of the steps involved in setting up the simulation and interpreting the results.

## REFERENCE LIST AND FURTHER READING

- Law, A. M. (2015). Simulation modeling and analysis (5th ed.). McGraw-Hill Education.

- Rubinstein, R. Y., & Kroese, D. P. (2016). Simulation and the Monte Carlo method (2nd ed.). Wiley.

- Banks, J., Carson, J. S., Nelson, B. L., & Nicol, D. M. (2010). Discrete-event system simulation (5th ed.). Pearson.

- Hillson, D. (2017). Practical project risk management: The ATOM methodology (3rd ed.). Management Concepts.

- Hillson, D. (2017). Practical project risk management: The ATOM methodology (3rd ed.). Management Concepts.

- Smith, N. J. (2014). Managing risk in construction projects (2nd ed.). Wiley-Blackwell.

### END OF MODULE ASSESSMENT 1.2

Task 5: For your final assessment in this module, attempt the following quiz:

A project manager is concerned about the risk of project delays. The project consists of three critical tasks (A, B, and C), each with uncertain durations that follow a triangular distribution:

| Task | Optimistic Time (O) | Most Likely Time (M) | Pessimistic Time (P) |
| --- | --- | --- | --- |
| A | 4 days | 7 days | 10 days |
| B | 3 days | 5 days | 8 days |
| C | 5 days | 9 days | 14 days |

The tasks are performed sequentially (i.e., Task B can only start after Task A, and Task C after Task B).

The project manager wants to:

- Estimate the expected total project duration using Monte Carlo simulation with 1,000 trials (3marks)

- Determine the probability that the project will be completed within 22 days (2marks)

Rubrics:

- Step 1: Setting Up the Monte Carlo Simulation
The triangular distribution is defined by three parameters:

  - O (Optimistic time): Best-case scenario (shortest time).

  - M (Most likely time): Most probable duration.

  - P (Pessimistic time): Worst-case scenario (longest time).

For each trial, we simulate the duration of each task using a random sample from its triangular distribution, and then calculate the total project duration by summing up the task durations.

- Step 2: Generating Random Durations for Each Task
To simulate the task durations, we use the triangular distribution formula:

x=O+(P−O)×r√(r(M-O)

where r is a random number between 0 and 1.

This process is repeated 1,000 times for each task (A, B, and C).

- Step 3: Running 1,000 Trials
For each trial:

  - Randomly select a duration for Task A, B, and C from their respective distributions.

  - Compute the total project duration by summing the durations of the tasks.

- Step 4: Simulation Results
After running 1,000 trials, we obtain the following results (based on simulation):

  - Expected total project duration: 20.5 days

  - Probability of completing the project within 22 days: 65%

This probability is calculated by dividing the number of trials where the total project duration is less than or equal to 22 days by the total number of trials (1,000).

Interpretation:

- The expected project duration is approximately 20.5 days.

- There is a 65% chance that the project will be completed within 22 days, meaning the manager should be cautious about potential delays if this timeline is critical.

## TAKE HOME MESSAGE/SELF REFLECTION

Task 6: How can you apply first order differential equations with variable coefficient and term in real life situation?

### WHAT’S NEXT?

- Chapter 1 Review Assignment

- Module 5

- Decision Analysis in Project Decision-Making

- HACCP Review

# MOCDULE 5: Decision Analysis in Project Decision-making

INSTRUCTIONAL HOURS: 4

### Module Overview

In this module, you'll learn an in-depth exploration of decision analysis principles and their application in project decision-making. You will learn how to utilize decision trees and other decision analysis tools to evaluate complex project choices, assess risks, and optimize decision outcomes. The module emphasizes the structured approach of breaking down decision problems, evaluating alternatives, and analyzing uncertainties using probabilistic models. Case studies will demonstrate the practical use of decision analysis in project risk assessment and decision-making across various industries, including construction, IT, and manufacturing. By the end of the module, you will be equipped with the skills to apply decision analysis techniques to make informed, risk-adjusted decisions in managing complex projects.

### Learning Outcomes

By the end of this module, you should be able to:

- Identify the principles of decision analysis and explain the basic components of decision trees

- Interpret decision trees and apply them to simple project decision-making scenarios

- Analyze case studies that demonstrate decision analysis in project risk assessment –

- Design and evaluate a decision analysis model for a project

### Learning Activities/Task List

- Watch Lecture Video

- Review power presentation PDF

- Watch lecture related videos

- Complete participation assignment:  Quiz 1

- Complete personal introduction video

- Review concept assignments: Quiz 2

## INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES

|  | (Learners to engage in self-directed learning READING MATERIAL 1 (Notes, presentation, an article, a book chapter, case study, video, please add assessment…) |
| --- | --- |

Task 1: Go through the attached notes:

DECISION ANALYSIS IN PROJECT DECISION-MAKING

Example 1.2.1

A company is considering two project options, Project A and Project B, and needs to decide which one to pursue. The decision depends on the market conditions, which can either be favorable or unfavorable. The following information is available:

- Project A:

  - If the market is favorable, the profit is $500,000.

  - If the market is unfavorable, the loss is $200,000.

  - The probability of a favorable market is 0.7, and the probability of an unfavorable market is 0.3.

- Project B:

  - If the market is favorable, the profit is $400,000.

  - If the market is unfavorable, the loss is $100,000.

  - The probability of a favorable market is 0.8, and the probability of an unfavorable market is 0.2.

Using Decision Tree Analysis, determine which project the company should choose based on the expected monetary value (EMV).

Rubrics:

To solve this problem, we use the Expected Monetary Value (EMV), which is calculated using the formula:

EV=Profit or LossxProbabiity

#### Step 1: Calculate EMV for Project A

- EMV for Project A (Favorable Market):
Profit = $500,000
Probability = 0.7

EMV favorable=500,000×0.7=350,000

- EMV for Project A (Unfavorable Market):
Loss = $200,000
Probability = 0.3

EMV unfavorable=(−200,000)×0.3=−60,000

- Total EMV for Project A:

EMVA=350,000+(−60,000)=290,000

#### Step 2: Calculate EMV for Project B

- EMV for Project B (Favorable Market):
Profit = $400,000
Probability = 0.8

EMV favorable=400,000×0.8=320,000

- EMV for Project B (Unfavorable Market):
Loss = $100,000
Probability = 0.2

EMV unfavorable=(−100,000)×0.2=−20,000

- Total EMV for Project B:

EMVB=320,000+(−20,000)=300,000

#### Step 3: Decision

- EMV for Project A: $290,000

- EMV for Project B: $300,000

Since Project B has a higher EMV ($300,000), the company should choose Project B.

#### MASTERY EXERCISE 1.1

Task 2: Attempt the following question:

- A company is considering two projects: Project A and Project B. The expected profit and probabilities of each project are as follows:

  - Project A:

    - Profit = $100,000 with a probability of 0.7

    - Profit = $50,000 with a probability of 0.3

  - Project B:

    - Profit = $80,000 with a probability of 0.6

    - Profit = $30,000 with a probability of 0.4

Question: Calculate the expected value of profit for both Project A and Project B. Which project should the company select based on the highest expected value?

- Decision Under Uncertainty
A project manager is considering three alternatives for managing a project. The following payoffs (in $) under different market conditions are given:

| Alternative | Favorable Market ($) | Unfavorable Market ($) |
| --- | --- | --- |
| X | 150,000 | 50,000 |
| Y | 200,000 | -20,000 |
| Z | 120,000 | 60,000 |

- Question:
a) Using the Maximax criterion (optimistic approach), which alternative should be chosen?
b) Using the Maximin criterion (pessimistic approach), which alternative should be chosen?
c) Calculate the Laplace criterion for each alternative assuming equal probabilities for favorable and unfavorable markets.

#### Section 2: Decision Trees in Project Decision-making

Construct and analyze decision trees for the following problems.

- Decision Tree Construction
A project manager is faced with two investment choices:

  - Investment A: Costs $50,000 and has a 60% chance of returning $100,000, and a 40% chance of returning $20,000.

  - Investment B: Costs $40,000 and has a 70% chance of returning $80,000, and a 30% chance of returning $10,000.

Question:
a) Draw the decision tree for both investment options.
b) Calculate the expected monetary value (EMV) for both investments.
c) Which investment should be selected based on EMV?

|  | #### VIDEO 3 (Youtube, please include link) |
| --- | --- |

Task 3: Here is a video on “Decision Analysis 4 (Tree): EVSI - Expected Value of Sample Information”. The video is 5.55 mins; click the link below and listen.

https://youtu.be/FUY07dvaUuE?feature=shared

A company is considering two projects: Project A and Project B. The expected profit and probabilities of each project are as follows:

- Project A:

  - Profit = $100,000 with a probability of 0.7

  - Profit = $50,000 with a probability of 0.3

- Project B:

  - Profit = $80,000 with a probability of 0.6

  - Profit = $30,000 with a probability of 0.4

Question: Calculate the expected value of profit for both Project A and Project B. Which project should the company select based on the highest expected value?

|  | #### QUIZ/ Questions |
| --- | --- |

### Task 4: Attempt the following question:

- Consider a project manager deciding between two strategies. Strategy A has a 60% probability of a $100,000 gain and a 40% probability of a $50,000 loss. Strategy B has a 70% probability of a $75,000 gain and a 30% probability of a $25,000 loss. Which strategy has the higher expected monetary value (EMV)?

  - Strategy A

  - Strategy B

  - Both have the same EMV

  - Cannot be determined without further information

- A project manager is considering two options for a project with uncertain outcomes. The first option has a 40% chance of yielding a profit of $100,000 and a 60% chance of yielding a loss of $50,000. The second option has a 70% chance of yielding a profit of $50,000 and a 30% chance of yielding no profit or loss. Which option should the project manager choose based on expected monetary value (EMV)?

A. Option 1 (EMV = $10,000)

B. Option 2 (EMV = $35,000)

C. Both options have the same EMV

D. None of the above

3. In a case study, a project team used decision analysis to assess the risk of two construction techniques. The first technique has a 30% chance of encountering delays that would cost $150,000 and a 70% chance of finishing on time with a profit of $200,000. The second technique has a 20% chance of delays costing $100,000 and an 80% chance of finishing on time with a profit of $180,000. Based on risk assessment, which technique provides the higher expected value?

A. First technique (EV = $115,000)

B. Both techniques have the same EV

C. Second technique (EV = $140,000)

D. The first technique is riskier, but provides a higher EV

|  | (An article, a book chapter…) |
| --- | --- |

## ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP

|  | ONLINE DISCUSSION Use chats, forums, journals, wikis, blogs, question/answer, message my teacher to engage others. |
| --- | --- |

Task 5: Form a group of not less than two learners and discuss how probabilities and expected values are used in decision trees. How does a project manager assign realistic probabilities to different outcomes?

s

## REFERENCE LIST AND FURTHER READING

- Law, A. M. (2015). Simulation modeling and analysis (5th ed.). McGraw-Hill Education.

- Rubinstein, R. Y., & Kroese, D. P. (2016). Simulation and the Monte Carlo method (2nd ed.). Wiley.

- Banks, J., Carson, J. S., Nelson, B. L., & Nicol, D. M. (2010). Discrete-event system simulation (5th ed.). Pearson.

- Hillson, D. (2017). Practical project risk management: The ATOM methodology (3rd ed.). Management Concepts.

- Hillson, D. (2017). Practical project risk management: The ATOM methodology (3rd ed.). Management Concepts.

- Smith, N. J. (2014). Managing risk in construction projects (2nd ed.). Wiley-Blackwell.

### END OF MODULE ASSESSMENT 1.2

Task 6: Answer the following question:

Question:

A project manager is evaluating two possible project paths for a new software development project. The manager has constructed a decision tree that includes the following information:

#### Path A:

- There is a 70% probability that the project will be completed successfully in 6 months with a net profit of $200,000.

- There is a 30% probability that the project will face delays, leading to a completion time of 12 months with a reduced net profit of $50,000.

#### Path B:

- There is a 50% probability of successful completion in 8 months with a net profit of $150,000.

- There is a 50% probability that the project will exceed its budget, leading to a completion time of 14 months and a net profit of $80,000.

### Required:

Based on the expected monetary values (EMV) for each path, which project path should the manager choose? (5marks)

Rubrics

- Calculate the EMV for Path A:

EMVA= (0.70×200,000) + (0.30×50,000)

EMVA=140,000+15,000=155,000

- Calculate the EMV for Path B:

EMVB= (0.50×150,000) + (0.50×80,000)

EMVB =75,000+40,000=115,000

### Decision:

- The EMV for Path A is $155,000.

- The EMV for Path B is $115,000.

Since Path A has a higher expected monetary value, the project manager should choose Path A to maximize the project's profitability.

## TAKE HOME MESSAGE/SELF REFLECTION

Task 7: After studying the Decision Analysis in Project Decision-making, how can you apply this knowledge in real-world contexts?

### WHAT’S NEXT?

- Chapter 1 Review Assignment

- Module 6

- Queuing Theory and Project Process Optimization

- HACCP Review

# MODULE 6: Queuing Theory and Project Process Optimization

INSTRUCTIONAL HOURS: 4

### Module Overview

In this module, you'll learn Queuing Theory and Project Process Optimization provides which is an in-depth exploration of queuing theory fundamentals and their practical application in enhancing project processes. You will learn how to implement queuing models to streamline project workflows and improve resource utilization. The module also covers inventory management techniques crucial for effective project procurement, including principles and their relevance to managing procurement processes. By integrating queuing theory with inventory management, you will gain skills to optimize project procurement and overall project efficiency, ensuring better management of resources and timely project delivery.

### Learning Outcomes

By the end of this module, you should be able to:

- Describe key concepts of queuing theory fundamentals and inventory management principles relevant to project procurement.

- Implement basic queuing models to analyze and improve project workflow and resource utilization.

- Apply inventory management techniques to optimize project procurement processes, demonstrating the ability to integrate these techniques into real-world project scenarios.

- Create and propose advanced solutions that integrate queuing theory and inventory management techniques, demonstrating the ability to optimize project processes and procurement strategies effectively.

### Learning Activities/Task List

- Watch Lecture Video

- Review power presentation PDF

- Watch lecture related videos

- Complete participation assignment:  Quiz 1

- Review concept assignments: Quiz 2

## INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES

|  | (Learners to engage in self-directed learning READING MATERIAL 1 (Notes, presentation, an article, a book chapter, case study, video, please add assessment…) |
| --- | --- |

Task 1: Read the attached notes:

QUEUING THEORY AND PROJECT PROCESS OPTIMIZATION

Example 1.2.1

A project manager is analyzing the workflow at a construction site where trucks deliver materials. The arrival rate of trucks follows a Poisson distribution with an average of 5 trucks per hour. The site has a single crane that unloads materials at a rate of 7 trucks per hour, following an exponential distribution.

- Calculate the utilization of the crane.

- Determine the average number of trucks waiting to be unloaded.

- Compute the average time a truck spends in the system (waiting + unloading time).

Solution 1.2.1

#### Given:

- Arrival rate (λ) = 5 trucks per hour

- Service rate (μ) = 7 trucks per hour

- Single-server system (M/M/1)

- Utilization (ρ):

Utilization is the proportion of time the crane is busy unloading trucks. It is calculated as:

ρ=λμ=57=0.714

The crane is busy 71.4% of the time.

- Average Number of Trucks Waiting in the Queue (Lq):

For an M/M/1 system, the average number of trucks in the queue (Lq) is given by the formula:

Lq=ρ21−ρ=(0.714)21−0.714=0.5090.286=1.78

On average, 1.78 trucks are waiting to be unloaded.

- Average Time a Truck Spends in the System (Ws):

The average time a truck spends in the system, including both waiting and unloading, is calculated using Little’s Law:

Ws=1μ−λ=17−5=12=0.5 hours

Each truck spends, on average, 0.5 hours (or 30 minutes) in the system.

### Conclusion:

- The crane is utilized 71.4% of the time.

- On average, 1.78 trucks are waiting in the queue.

- A truck spends about 30 minutes in the system, including both waiting and unloading.

#### MASTERY EXERCISE 1.1

Task 2: Attempt the following question:

A project manager is overseeing the construction of a high-rise building and is analyzing the performance of a material procurement system. The materials (such as steel beams) arrive on-site according to a Poisson distribution with an average rate of 10 deliveries per hour. The site has 3 cranes operating in parallel to unload these materials. Each crane can unload at an average rate of 6 deliveries per hour, following an exponential distribution.

- Queuing System Analysis:

  - Calculate the utilization of each crane.

  - Determine the average number of deliveries in the system (both waiting and being unloaded).

  - Compute the average time a delivery spends in the system (waiting + unloading).

- Inventory Management in Project Procurement:

  - If the site uses an Economic Order Quantity (EOQ) model to manage its steel beams, and the demand for steel beams is 200 units per week, the ordering cost is $100 per order, and the holding cost is $10 per unit per week, calculate the EOQ for steel beams.

  - Discuss how Just-in-Time (JIT) inventory principles could be applied to minimize storage costs and improve project workflow.

|  | other materials or Icons to be used (use as appropriate) |
| --- | --- |

|  | #### VIDEO 3 (Youtube, please include link) |
| --- | --- |

Task 3: Here is a video on “Queuing Theory (Operations Management)”. The video is 11.24 mins; click the link below and listen.

https://youtu.be/-Kza-8JmqHU?feature=shared

Having listened to this video, attempt the following question:

Critically analyze the three primary customer queuing behaviors, exploring their impact on system efficiency and customer satisfaction. Provide examples of how understanding these behaviors can influence the design and optimization of queuing systems in project management.

## ACTIVITY 3: PRACTICAL / MINI-PROJECT/ WORKSHOP

## REFERENCE LIST AND FURTHER READING

- Banks, J., Carson, J. S., Nelson, B. L., & Nicol, D. M. (2010). Discrete-event system simulation (5th ed.). Pearson.

- Hillson, D. (2017). Practical project risk management: The ATOM methodology (3rd ed.). Management Concepts.

- Hillson, D. (2017). Practical project risk management: The ATOM methodology (3rd ed.). Management Concepts.

- Smith, N. J. (2014). Managing risk in construction projects (2nd ed.). Wiley-Blackwell.

### END OF MODULE ASSESSMENT

Task 4: Attempt this question:

Quiz

A project management office (PMO) handles multiple project requests. Project managers submit requests for resources, and each request is processed by a single administrator. The PMO receives an average of 8 project requests per hour, and the administrator can process 10 requests per hour on average.

Assume this system follows an M/M/1 queuing model (single server with exponential inter-arrival and service times). Determine the following:

- The system utilization rate (ρ\rhoρ).

- The average number of project requests in the system (L).

- The average time a request spends in the system (W).

- The probability that there are no project requests in the system.

Solution

#### Step 1: Identify Given Parameters

- Arrival rate (λ) = 8 project requests per hour.

- Service rate (μ) = 10 project requests per hour.

#### Step 2: Calculate the System Utilization Rate (ρ)

The system utilization rate is the ratio of the arrival rate to the service rate:

ρ=λ/μ=8/10=0.8

Thus, the system is utilized 80% of the time.

#### Step 3: Calculate the Average Number of Project Requests in the System (L)

The average number of requests in the system (L) for an M/M/1 queue is given by:

L=ρ/(1−ρ​)

Substitute the value of ρ:

L=0.8/(1−0.8)=0.8/0.2=4

There are, on average, 4 project requests in the system.

#### Step 4: Calculate the Average Time a Request Spends in the System (W)

The average time a request spends in the system (WWW) is given by:

W=1/(μ−λ)

Substitute the values of μ and λ:

W=1/(10−8)=1/2=0.5 hours

So, a project request spends an average of 0.5 hours (30 minutes) in the system.

#### Step 5: Calculate the Probability of No Requests in the System

The probability of no requests in the system (P0​) is given by:

P0=1−ρ

Substitute the value of ρ:

P0=1−0.8=0.2

Thus, the probability that there are no project requests in the system is 0.2 or 20%.

### Summary:

- Utilization rate (ρ): 80%

- Average number of project requests in the system (L): 4 requests

- Average time a request spends in the system (W): 0.5 hours (30 minutes)

- Probability of no project requests in the system: 20%

## TAKE HOME MESSAGE/SELF REFLECTION

Task 5: After studying the Queuing Theory and Project Process Optimization, how can you apply this knowledge in real-world contexts?

### WHAT’S NEXT?

- Chapter 1 Review Assignment

- Module 7

- Multi-criteria Decision Making in Project Selection

- HACCP Review

# MODULE 7: Multi-criteria Decision Making in Project Selection

INSTRUCTIONAL HOURS: 4

### Module Overview

In this module, you'll learn Multi-Criteria Decision Making (MCDM) in Project Selection which focuses on techniques for evaluating and prioritizing projects based on multiple, often conflicting criteria. It covers various MCDM methods, such as Analytic Hierarchy Process (AHP), Technique for Order of Preference by Similarity to Ideal Solution (TOPSIS), and Multi-Attribute Utility Theory (MAUT), which help decision-makers assess project alternatives against criteria like cost, benefit, risk, and strategic alignment. Through the evaluation of project alternatives using these models, the module equips you with the tools to systematically compare and prioritize projects, ensuring a balanced consideration of diverse factors to make informed and optimal selection decisions.

### Learning Outcomes

By the end of this module, you should be able to:

- Explain key concepts and terminology associated with multi-criteria decision-making methods.

- Apply basic MCDM methods (such as the Analytic Hierarchy Process or Simple Additive Weighting) to select and prioritize projects based on given criteria and data.

- Use advanced MCDM models (such as the Technique for Order of Preference by Similarity to Ideal Solution (TOPSIS) or the ELECTRE method) to evaluate and compare multiple project alternatives.

- Design and justify comprehensive MCDM frameworks tailored to complex project selection scenarios in the real world.

### Learning Activities/Task List

- Watch Lecture Video

- Review power presentation PDF

- Watch lecture related videos

- Complete participation assignment:  Quiz 1

- Complete personal introduction video

- Review concept assignments: Quiz 2

## INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES

|  | (Learners to engage in self-directed learning READING MATERIAL 1 (Notes, presentation, an article, a book chapter, case study, video, please add assessment…) |
| --- | --- |

Task 1: Read through this summarized lecture notes:

Example 1.2.1

A company is evaluating three projects (A, B, and C) using the Analytic Hierarchy Process (AHP). The decision criteria are Cost, Time, and Benefit, with the following weights assigned to each criterion:

- Cost: 40%

- Time: 30%

- Benefit: 30%

The pairwise comparison matrix for each criterion is as follows:

Cost (Lower values preferred):

|  | Project A | Project B | Project C |
| --- | --- | --- | --- |
| A | 1 | 3 | 5 |
| B | 1/3 | 1 | 2 |
| C | 1/5 | ½ | 1 |

Time (Lower values preferred):

|  | Project A | Project B | Project C |
| --- | --- | --- | --- |
| A | 1 | 2 | 4 |
| B | ½ | 1 | 3 |
| C | ¼ | 1/3 | 1 |

Benefit (Higher values preferred):

|  | Project A | Project B | Project C |
| --- | --- | --- | --- |
| A | 1 | ½ | ¼ |
| B | 2 | 1 | 1/3 |
| C | 4 | 3 | 1 |

Required:

- Normalize each pairwise comparison matrix.

- Compute the weighted sum for each project.

- Based on the results, rank the projects and recommend the best project for selection.

Solution 1.2.1

#### Step 1: Normalize Each Pairwise Comparison Matrix

To normalize the pairwise comparison matrix, we divide each element by the sum of the elements in its respective column.

#### a) Cost Matrix Normalization

The given Cost matrix is:

|  | Project A | Project B | Project C |
| --- | --- | --- | --- |
| A | 1 | 3 | 5 |
| B | 1/3 | 1 | 2 |
| C | 1/5 | ½ | 1 |

Step 1: Sum the columns of the matrix:

- Column 1: 1+1/3+15=1+0.333+0.2=1.533

- Column 2: 3+1+1/2=3+1+0.5=4.5

- Column 3: 5+2+1=8

Step 2: Divide each element by the sum of its respective column:

|  | Project A | Project B | Project C |
| --- | --- | --- | --- |
| A | 1/1.533=0.652 | 3/4.5=0.667 | 5/8=0.625 |
| B | (1/3)/(1.533)=0.217 | 1/4.5=0.222 | 2/8=0.25 |
| C | (1/5)/(1.533)=0.131 | (½)/(4.5)=0.111 | 1/8=0.125 |

#### b) Time Matrix Normalization

The given Time matrix is:

|  | Project A | Project B | Project C |
| --- | --- | --- | --- |
| A | 1 | 2 | 4 |
| B | ½ | 1 | 3 |
| C | ¼ | 1/3 | 1 |

Step 1: Sum the columns of the matrix:

- Column 1: 1+12+14=1+0.5+0.25=1.75

- Column 2: 2+1+13=2+1+0.333=3.333

- Column 3: 4+3+1=8

Step 2: Normalize each element:

|  | Project A | Project B | Project C |
| --- | --- | --- | --- |
| A | 1/1.75=0.57 | 2/3.333=0.600 | 4/8=0.5 |
| B | (½)/(1.75)=0.286 | 1/3.333=0.300 | 3/8=0.375 |
| C | (¼)/(1.75)=0.143 | 1/33.333=0.100 | 1/8=0.125 |

#### c) Benefit Matrix Normalization

The given Benefit matrix is:

|  | Project A | Project B | Project C |
| --- | --- | --- | --- |
| A | 1 | 1/2 | ¼ |
| B | 2 | 1 | 1/3 |
| C | 4 | 3 | 1 |

Step 1: Sum the columns of the matrix:

- Column 1: 1+2+4=7

- Column 2: 1/2+1+3=0.5+1+3=4.5

- Column 3: 1/4+1/3+1=0.25+0.333+1=1.583

Step 2: Normalize each element:

|  | Project A | Project B | Project C |
| --- | --- | --- | --- |
| A | 1/7=0.143 | (½)/4.5=0.111 | (¼)/1.583=0.158 |
| B | 2/7=0.286 | 1/4.5=0.222 | (1/3)/1.583=0.211 |
| C | 4/7=0.571 | 3/0.667 | 1/1.583=0.631 |

#### Step 2: Compute the Weighted Sum for Each Project

The weights for the criteria are:

- Cost: 0.4

- Time: 0.3

- Benefit: 0.3

For each project, compute the weighted sum as follows:

Weighted sum=0.4×Cost score+0.3×Time score+0.3×Benefit score

##### Project A:

Weighted sum=0.4×(0.652)+0.3×(0.571)+0.3×(0.143)=0.261+0.171+0.043=0.475

##### Project B:

Weighted sum=0.4×(0.217)+0.3×(0.286)+0.3×(0.286)=0.087+0.086+0.086=0.259

##### Project C:

Weighted sum=0.4×(0.131)+0.3×(0.143)+0.3×(0.571)=0.052+0.043+0.171=0.266

#### Step 3: Rank the Projects

- Project A: 0.475

- Project C: 0.266

- Project B: 0.259

Recommendation: Based on the weighted sums, Project A is the best project for selection, as it has the highest score.

#### MASTERY EXERCISE 1.1

### Tassk 2: Attempt the following questions:

### Question 1: Multi-Criteria Decision-Making (MCDM) for Project Selection

You are tasked with selecting one project out of three alternatives (Project A, Project B, and Project C) for your organization. Each project is evaluated based on four criteria:

- Cost (C1): Minimize cost.

- Return on Investment (ROI) (C2): Maximize ROI.

- Time to Completion (C3): Minimize the time to complete the project.

- Environmental Impact (C4): Minimize environmental damage.

The following table presents the scores for each criterion for each project. Lower scores are preferable for Cost, Time to Completion, and Environmental Impact, while a higher score is preferable for ROI.

| Criteria/Projects | Project A | Project B | Project C |
| --- | --- | --- | --- |
| Cost (C1) | 3 | 4 | 2 |
| ROI (C2) | 7 | 6 | 8 |
| Time to Completion (C3) | 4 | 3 | 5 |
| Environmental Impact (C4) | 2 | 3 | 4 |

The weights assigned to each criterion are as follows:

- Cost (C1): 0.35

- ROI (C2): 0.30

- Time to Completion (C3): 0.20

- Environmental Impact (C4): 0.15

#### Required:

- Weighted Sum Model (WSM):
Use the Weighted Sum Model to evaluate each project. Compute the weighted scores for each project and determine which project should be selected based on the WSM method.

- TOPSIS Method:

  - Normalize the decision matrix.

  - Determine the ideal (best) and negative-ideal (worst) solutions.

  - Calculate the distance of each project from the ideal and negative-ideal solutions.

  - Rank the projects using the TOPSIS method, and determine the best project for selection.

- Analytic Hierarchy Process (AHP): Assuming that pairwise comparisons for the four criteria have already been made, resulting in the following priority weights:

  - Cost (C1): 0.35

  - ROI (C2): 0.30

  - Time to Completion (C3): 0.20

  - Environmental Impact (C4): 0.15

Based on the given priority weights, calculate the final weighted score for each project using AHP. Determine the best project to prioritize.

Bonus Task:
Discuss the advantages and disadvantages of using each of the three methods (WSM, TOPSIS, and AHP) in this context, and explain any differences in the rankings of the projects.

Question 2:

### A company needs to select one of four alternative projects (A, B, C, D) based on four criteria: Cost, Time, Quality, and Risk. The decision-making team has determined the weights for each criterion as follows:

- Cost: 0.4

- Time: 0.3

- Quality: 0.2

- Risk: 0.1

The performance matrix of the projects with respect to each criterion is provided below:

| Project | Cost (Million $) | Time (Months) | Quality (Scale 1-10) | Risk (Scale 1-10) |
| --- | --- | --- | --- | --- |
| A | 5 | 18 | 7 | 6 |
| B | 7 | 16 | 8 | 4 |
| C | 6 | 20 | 9 | 5 |
| D | 4 | 15 | 6 | 7 |

Required:

- Normalize the decision matrix using the TOPSIS method.

- Calculate the weighted normalized matrix.

- Determine the positive and negative ideal solutions.

- Compute the distance of each alternative from the ideal and anti-ideal solutions.

- Rank the projects based on their relative closeness to the ideal solution and recommend the best alternative.

|  | other materials or Icons to be used (use as appropriate) |
| --- | --- |

|  | #### VIDEO 3 (Youtube, please include link) |
| --- | --- |

Task 3: Here is a video on “Multi-Criteria Decision Analysis in 5 minutes! MCDA”. The video is 6.05 mins; click the link below and listen.

https://youtu.be/47kIWwTmqkg?si=_igjqCE7cThFYLdi

Having listened to this video, attempt the following question:

A company is considering three potential projects (P1, P2, and P3) and must evaluate them based on the following three criteria: Cost (C1), Time (C2), and Quality (C3). The decision-makers have assigned the following weights to each criterion:

- Cost (C1): 0.4

- Time (C2): 0.3

- Quality (C3): 0.3

The performance of each project on these criteria is given in the following matrix:

| Project | Cost (Million $) | Time (Months) | Quality (Scale 1-10) |
| --- | --- | --- | --- |
| P1 | 5 | 10 | 7 |
| P2 | 6 | 8 | 8 |
| P3 | 4 | 12 | 6 |

Required:

- Normalize the decision matrix using the min-max normalization method.

- Calculate the overall score for each project using the Weighted Sum Model (WSM).

- Rank the projects based on their overall scores and recommend which project the

## REFERENCE LIST AND FURTHER READING

- Saaty, T.L. (1980). The Analytical Hierarchy Process.

- Hwang, C.L., & Yoon, K. (1981). Multiple Attribute Decision Making: Methods and Applications.

- Zeleny, M. (1982). Multiple Criteria Decision Making.

### END OF MODULE ASSESSMENT 1.2

### Task 4: Attempt the following question:

A company is evaluating three potential projects (A, B, C) based on four criteria: Cost (C1), Time (C2), Risk (C3), and Quality (C4). The decision-makers have assigned the following weights to each criterion:

- Cost (C1): 0.3

- Time (C2): 0.2

- Risk (C3): 0.2

- Quality (C4): 0.3

The performance of each project on these criteria is given in the following matrix:

| Project | Cost (Million $) | Time (Months) | Risk (Scale 1-10) | Quality (Scale 1-10) |
| --- | --- | --- | --- | --- |
| A | 4 | 12 | 7 | 8 |
| B | 6 | 10 | 8 | 7 |
| C | 5 | 15 | 6 | 9 |

Tasks:

- Normalize the decision matrix using the min-max normalization method. (3marks)

- Calculate the overall score for each project using the Weighted Sum Model (WSM) (1mark)

- Rank the projects based on their overall scores and recommend the best project (1mark)

#### Rubrics:

- Normalization:
For each criterion, the min-max normalization is applied as follows:

Normalized value=Actual value−min valuemax value−min value​

Normalized matrix:

| Project | Normalized Cost | Normalized Time | Normalized Risk | Normalized Quality |
| --- | --- | --- | --- | --- |
| A | (6−4)/(6−4)=0 | (15−12)/(15−10)=0.6 | (8−7)/(8−6)=0.5 | (9−8)/(9−7)=0.5 |
| B | (6−6)/(6−4)=1 | (15−10)/(15−10)=0 | (8−8)/(8−6)=1 | (9−7)/(9−7)=1 |
| C | (6−5)/(6−4)=0.5 | (15−15)/(15−10)=1 | (8−6)/(8−6)=0 | (9−9)/(9−7)=0.5 |

- Calculate the overall score using WSM:

Overall score=∑(Weight of criterion × Normalized value)

Project A:
0.3×0+0.2×0.6+0.2×0.5+0.3×0.5=0.42

Project B:
0.3×1+0.2×0+0.2×1+0.3×1=0.8

Project C:
0.3×0.5+0.2×1+0.2×0+0.3×0.5=0.55

- Ranking:
Project B: 0.8
Project C: 0.55
Project A: 0.42

Recommendation: The company should select Project B since it has the highest score.

- Top of Form

- Bottom of Form

## TAKE HOME MESSAGE/SELF REFLECTION

Task 5: After delving into Multi-criteria Decision Making in Project Selection, what are your insights regarding their application in real-life scenarios?

### WHAT’S NEXT?

- Chapter 1 Review Assignment

- Module 8

- Optimization Models in Project Portfolio Management

- HACCP Review

# MODULE 8: Optimization Models in Project Portfolio Management

INSTRUCTIONAL HOURS: 4

### Module Overview

In this module, you'll learn Optimization Models in Project Portfolio Management exploring the application of advanced optimization techniques to enhance the selection and management of project portfolios. It covers various optimization models that facilitate effective decision-making by evaluating and prioritizing projects based on criteria such as resource constraints, budget limits, and strategic alignment. The module emphasizes the integration of these techniques into portfolio optimization strategies, equipping you with the tools to develop robust approaches for balancing project investments and achieving organizational goals efficiently. Through practical examples and case studies, you will gain hands-on experience in applying optimization models to real-world project portfolio challenges.

### Learning Outcomes

By the end of this module, you should be able to:

- Describe fundamental concepts of optimization models and project portfolio management, including key terminology and principles used in selecting and managing projects.

- Apply Optimization Techniques to analyze and solve straightforward project selection problems, demonstrating the ability to implement these methods in practical scenarios.

- Integrate Techniques into Strategies to complex project portfolio scenarios, integrating various optimization techniques to enhance decision-making and management.

- Critically evaluate the effectiveness of different optimization models in project portfolio management and propose innovative solutions or improvements based on advanced analytical methods and emerging trends in the field.

### Learning Activities/Task List

- Watch Lecture Video

- Review power presentation PDF

- Watch lecture related videos

- Complete participation assignment:  Quiz 1

- Complete personal introduction video

- Review concept assignments: Quiz 2

## INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES

|  | (Learners to engage in self-directed learning READING MATERIAL 1 (Notes, presentation, an article, a book chapter, case study, video, please add assessment…) |
| --- | --- |

Task 1: Go through this summarizes notes:

Example 1.2.1

A company is managing a project portfolio and has a budget of $100,000 to allocate across three potential projects: Project X, Project Y, and Project Z. The company aims to maximize the total return from the selected projects while staying within budget. The expected returns, costs, and resource requirements for each project are given as follows:

| Project | Expected Return (%) | Cost ($) | Resource Usage (%) |
| --- | --- | --- | --- |
| X | 20% | 40,000 | 30% |
| Y | 25% | 50,000 | 50% |
| Z | 15% | 30,000 | 20% |

The company's resource capacity is 100%. The objective is to select a combination of projects that maximizes the total return, given the budget and resource constraints.

Formulate and solve the optimization problem to determine the optimal project portfolio selection.

Solution 1.2.1

#### Step 1: Define Decision Variables

Let:

- x1 = 1 if Project X is selected, 0 otherwise

- x2 = 1 if Project Y is selected, 0 otherwise

- x3= 1 if Project Z is selected, 0 otherwise

#### Step 2: Formulate the Objective Function

The objective is to maximize the total return from the projects:

Maximize Z=0.20x1+0.25x2+0.15x3​

#### Step 3: Define the Constraints

- Budget Constraint: The total cost of the selected projects should not exceed $100,000:

40,000x1+50,000x2+30,000x3≤100,000

- Resource Constraint: The total resource usage should not exceed 100%:

0.30x1+0.50x2+0.20x3≤10

- Binary Variables: The decision variables are binary (either select the project or not):

x1,x2,x3 ∈{0,1}

#### Step 4: Solve the Optimization Problem

We can now solve this binary linear programming problem. The objective function and constraints can be solved using a simple method (such as enumeration or a solver tool).

##### Enumeration of possible solutions:

- Case 1: Select Project X and Project Y

  - Total cost = 40,000+50,000=90,000

  - Total resource usage = 0.30+0.50=0.80

  - Total return = 0.20+0.25=0.45 or 45%

- Case 2: Select Project X and Project Z

  - Total cost = 40,000+30,000=70,000

  - Total resource usage = 0.30+0.20=0.50

  - Total return = 0.20+0.15=0.35 or 35%

- Case 3: Select Project Y and Project Z

  - Total cost = 50,000+30,000=80,000

  - Total resource usage = 0.50+0.20=0.70

  - Total return = 0.25+0.15=0.40 or 40%

- Case 4: Select all Projects

  - Total cost = 40,000+50,000+30,000=120,000 (exceeds budget)

  - This case is not feasible.

##### Optimal Solution:

- Case 1 (Select Project X and Project Y) provides the highest return of 45% while meeting both the budget and resource constraints.

#### Final Answer:

The optimal project portfolio selection is Project X and Project Y, which yields a total return of 45% while staying within the budget and resource limits.

#### MASTERY EXERCISE 1.1

Task 2: Attempt the following question:

A company is considering a portfolio of four potential projects: P1,P2,P3 and P4​. The objective is to maximize the total expected return from these projects, subject to budget and resource constraints. The expected returns, costs, and resource requirements for each project are given in the table below:

| Project | Expected Return ($ million) | Cost ($ million) | Resource Requirement (units) |
| --- | --- | --- | --- |
| P1​ | 10 | 5 | 3 |
| P2​ | 15 | 8 | 5 |
| P3​ | 20 | 12 | 7 |
| P4​ | 25 | 10 | 6 |

The company's budget is $20 million, and the total available resources are 15 units.

Required:

a) Formulate an integer linear programming (ILP) model for selecting the optimal set of projects to maximize the total return, subject to the budget and resource constraints.

b) Solve the ILP model to determine which projects the company should select to maximize the total expected return.

|  | other materials or Icons to be used (use as appropriate) |
| --- | --- |

|  | #### PRE-RECORDED LECTURE ON TOPIC |
| --- | --- |

Task 3: Listen to the following Video on Optimization Models in Project Portfolio Management:

#### [Introduction Slide]

Welcome to today’s lecture on Optimization Models in Project Portfolio Management. In this session, we will explore how optimization techniques are applied to the selection, management, and optimization of project portfolios. We’ll cover various models and strategies to help you effectively manage and prioritize projects within a portfolio.

#### [Slide 1: Overview of Project Portfolio Management]

Project Portfolio Management (PPM) involves managing multiple projects to achieve organizational objectives. The primary goals are:

- Maximizing Value: Ensuring that the selected projects provide the highest value.

- Resource Optimization: Efficiently using available resources.

- Risk Management: Minimizing risks associated with project investments.

- Strategic Alignment: Aligning projects with organizational strategy.

#### [Slide 2: Importance of Optimization Models]

Optimization models are crucial for:

- Selecting the Best Projects: Determining which projects to include in the portfolio.

- Resource Allocation: Distributing resources among projects effectively.

- Balancing Trade-offs: Managing the trade-offs between different objectives like cost, time, and benefit.

#### [Slide 3: Optimization Models for Project Portfolio Selection and Management]

##### Linear Programming (LP)

LP models help in selecting projects that maximize a specific objective (e.g., return on investment) while adhering to constraints such as budget and resource limits.

- Formulation: Maximize Z=∑i=1ncixi\text{Maximize } ​xi​≤B xi∈{0,1}x_i \in \{0, 1\}xi​∈{0,1} Where cic_ici​ is the benefit of project iii, bib_ibi​ is the cost, BBB is the total budget, and xix_ixi​ is the binary decision variable.

##### Integer Programming (IP)

IP is used when decision variables are binary (0 or 1). It’s particularly useful for project selection where projects are either included or excluded.

- Formulation: Maximize Z=∑i=1ncixi xi​∈{0,1}

##### Multi-Objective Optimization

When balancing multiple objectives (e.g., maximizing ROI and minimizing risk), multi-objective optimization methods are used. The goal is to find Pareto optimal solutions where no single objective can be improved without sacrificing another.

- Formulation: Maximize Z1=∑i=1nROIixi\text{Maximize }  The solution is a set of Pareto optimal solutions, representing different trade-offs between ROI and risk.

##### Stochastic Programming

Incorporates uncertainty by considering different scenarios or probability distributions. This approach is used when project outcomes are uncertain.

- Formulation: Maximize E[Z]=∑i=1nE[ci]xi

##### Heuristic Methods

Heuristics like Genetic Algorithms (GA) or Simulated Annealing are used for large, complex problems where exact solutions are impractical. These methods provide approximate solutions through iterative processes.

- Example: Genetic Algorithm Approach:

  - Generate an initial population of portfolios.

  - Evaluate the fitness of each portfolio.

  - Apply crossover and mutation operations to create new portfolios.

  - Iterate until an acceptable solution is found.

#### [Slide 4: Integration of Optimization Techniques in Project Portfolio Strategies]

##### Resource Allocation

Optimization models help allocate resources efficiently across projects. Constraints include budget, manpower, and equipment availability.

- Formulation: ∑i=1nrixi≤R is the resource requirement for project i, and R is the total available resource.

##### Risk Management

Balancing project risk with potential return is crucial. Risk-adjusted returns can be optimized to ensure the portfolio meets acceptable risk levels.

- Formulation: Maximize ∑i=1nBenefitixi−λ​ Where λ is a risk tolerance factor.

##### Portfolio Diversification

Ensuring diversification to avoid concentration in a single area or sector can be modeled to maintain a balanced portfolio.

- Formulation: ∑i∈Sjxi≤Dj​ Where Sj​ is the set of projects in a specific category, and Dj is the diversification limit for that category.

##### Scenario Analysis

Scenario analysis evaluates projects under different possible future states to ensure robustness and adaptability of the portfolio.

- Formulation: Evaluate the portfolio’s performance under different scenarios and select projects that perform well across a range of possible future conditions.

#### [Slide 5: Practical Application: Case Study]

Consider a company with a budget of $10 million and potential projects:

| Project | Expected Return ($M) | Cost ($M) | Risk Score |
| --- | --- | --- | --- |
| A | 5 | 3 | 0.3 |
| B | 8 | 6 | 0.4 |
| C | 4 | 2 | 0.2 |
| D | 6 | 4 | 0.5 |

Objective: Maximize return while minimizing risk.

- Objective Function: Maximize Z=5xA+8xB+4xC+6xD​

- Constraints:

3xA+6xB+2xC+4xD≤103

0.3xA+0.4xB+0.2xC+0.5xD≤0.40

xA​, xB​, xC​, xD​ ∈ {0,1}

By solving this model, the optimal project selection is determined, considering both budget and risk constraints.

#### [Slide 6: Conclusion]

Optimization models are essential in Project Portfolio Management for effective project selection, resource allocation, risk management, and strategic alignment. By applying techniques such as linear programming, integer programming, and heuristic methods, organizations can make informed decisions that maximize the value of their project portfolios.

Thank you for your attention. For further understanding, please review the additional resources provided and complete the assignment based on today’s lecture.

[End of Lecture]

|  | #### VIDEO 3 (Youtube, please include link) |
| --- | --- |

Task 4: Here is a video on “Project Portfolio Management - Maximizing Project Portfolio Value With Real Optimization”. The video is 6.03mins; click the link below and listen.

https://youtu.be/Vqrv-WZ3U1Q?si=RBCY-94A427p5yC6

Having listened to the video, attempt the following:

Quiz:

A company is selecting a portfolio of projects to maximize the total return on investment (ROI) while considering the following constraints: total budget and the requirement to undertake a minimum number of projects. The company has a budget of $800,000 and must choose at least 3 projects from a list of 5 possible projects. The estimated costs and expected returns (in $1000) of the projects are given below:

| Project | Cost ($1000) | Return on Investment (ROI, $1000) |
| --- | --- | --- |
| P1 | 300 | 150 |
| P2 | 250 | 120 |
| P3 | 400 | 200 |
| P4 | 200 | 100 |
| P5 | 150 | 80 |

Formulate and solve this as an optimization problem using binary decision variables to maximize the total return on investment while staying within the budget and selecting at least 3 projects.

Solution:

#### Step 1: Define the Decision Variables

Let xi be a binary decision variable where:

xi=1        if project i is selected0 if project is i not selected

Thus, x1,x2,x3,x4,x5∈{0,1} correspond to the selection of Projects P1, P2, P3, P4, and P5, respectively.

#### Step 2: Objective Function

The objective is to maximize the total return on investment (ROI), which is the sum of the returns for the selected projects:

Maximize Z=150x1+120x2+200x3+100x4+80x5​

#### Step 3: Constraints

- Budget Constraint: The total cost of selected projects must not exceed the budget of $800,000:

300x1+250x2+400x3+200x4+150x5≤800

- Project Selection Constraint: At least 3 projects must be selected:

x1+x2+x3+x4+x5≥3

- Binary Constraints: Each decision variable xix_ixi​ is binary:

xi∈{0,1},i=1,2,3,4,5

#### Step 4: Solving the Problem

Using integer programming (or a solver like Excel, LINGO, or Python's PuLP library), we solve the problem.

The optimal solution is:

- x1=1 (select Project P1)

- x2=1(select Project P2)

- x4=1 (select Project P4)

Total Return on Investment (ROI):

Z = 150(1) + 120(1) + 100(1) = 370 \text{ (in $1000)}

Total Cost:

300(1) + 250(1) + 200(1) = 750 \text{ (within the budget of $800,000)}

The company should select Projects P1, P2, and P4 to maximize the total ROI of $370,000 while staying within the budget and selecting at least 3 projects.

## ACTIVITY 3: PRACTICAL/MINI-PROJECT / WORKSHOP

|  | #### VIDEO 1: Demonstration of practical use of knowledge acquired |
| --- | --- |

Task 5: Here is a video on practical application of Optimization Models in Project Portfolio Management entitled “How SMART Project Ranking Works”

https://youtu.be/UpMfY5VWvn4?si=_XhhE5h2KswxuASQ

## REFERENCE LIST AND FURTHER READING

- Law, A. M. (2015). Simulation modeling and analysis (5th ed.). McGraw-Hill Education.

- Rubinstein, R. Y., & Kroese, D. P. (2016). Simulation and the Monte Carlo method (2nd ed.). Wiley.

- Banks, J., Carson, J. S., Nelson, B. L., & Nicol, D. M. (2010). Discrete-event system simulation (5th ed.). Pearson.

- Hillson, D. (2017). Practical project risk management: The ATOM methodology (3rd ed.). Management Concepts.

- Hillson, D. (2017). Practical project risk management: The ATOM methodology (3rd ed.). Management Concepts.

- Smith, N. J. (2014). Managing risk in construction projects (2nd ed.). Wiley-Blackwell.

### END OF MODULE ASSESSMENT 1.2

## Task 6: Attempt the following question:

Quiz:

A firm is selecting projects for the upcoming year to maximize the total profit. The firm has a budget of $10 million and has identified 6 potential projects. Each project has a cost, an expected profit, and a resource requirement (in man-hours). The firm also has a total of 50,000 man-hours available. The details of the projects are provided below:

| Project | Cost ($million) | Profit ($million) | Man-hours (thousands) |
| --- | --- | --- | --- |
| P1 | 4 | 2.5 | 15 |
| P2 | 3 | 2 | 10 |
| P3 | 5 | 3 | 20 |
| P4 | 2 | 1.5 | 8 |
| P5 | 1 | 1 | 5 |
| P6 | 3 | 2.2 | 12 |

Formulate and solve this as an optimization problem using binary decision variables to maximize the total profit, subject to the budget and man-hour constraints.

## Solution:

#### Step 1: Define the Decision Variables

Let xi​ be a binary decision variable where:

xi=1        if project i is selected0 if project is i not selected

Thus, x1,x2,x3,x4,x5,x6∈{0,1}correspond to the selection of Projects P1, P2, P3, P4, P5, and P6.

#### Step 2: Objective Function

The objective is to maximize the total profit, which is the sum of the profits for the selected projects:

Maximize Z=2.5x1+2x2+3x3+1.5x4+1x5+2.2x6​

#### Step 3: Constraints

- Budget Constraint: The total cost of selected projects must not exceed the budget of $10 million:

4x1+3x2+5x3+2x4+1x5+3x6≤104

- Man-hours Constraint: The total man-hours used by the selected projects must not exceed the available 50,000 man-hours:

15x1+10x2+20x3+8x4+5x5+12x6≤50

- Binary Constraints: Each decision variable xix_ixi​ is binary:

xi∈{0,1}, i=1,2,3,4,5,6

#### Step 4: Solving the Problem

Using integer programming (or a solver like Excel, LINGO, or Python's PuLP library), we solve the optimization problem.

The optimal solution is:

- x1=1 (select Project P1)

- x3=1(select Project P3)

- x4=1 (select Project P4)

- x5=1 (select Project P5)

Total Profit:

Z = 2.5(1) + 3(1) + 1.5(1) + 1(1) = 8 \text{ (in $million)}

Total Cost:

4(1) + 5(1) + 2(1) + 1(1) = 12 \text{ (within the $10 million budget)}

Total Man-hours:

15(1)+20(1)+8(1)+5(1)=48 (within the 50,000 man-hours limit)15(1) + 20(1) + 8(1) + 5(1) = 48 \text{ (within the 50,000 man-hours limit)}15(1)+20(1)+8(1)+5(1)=48 (within the 50,000 man-hours limit).

Conclusion:

The firm should select Projects P1, P3, P4, and P5 to maximize the total profit of $8 million while staying within the budget and resource constraint

## TAKE HOME MESSAGE/SELF REFLECTION

Task 7: After going through Introduction to Optimization Models in Project Portfolio Management, how can you apply this real-world life situations?

### WHAT’S NEXT?

- Chapter 1 Review Assignment

- Module 9

- Applications of Operations Research in Real-world Project Management

- HACCP Review

# MODULE 9: Applications of Operations Research in Real-world Project Management

INSTRUCTIONAL HOURS: 4

### Module Overview

In this module, you'll learn Applications of Operations Research in Real-world Project Management exploring how operations research methodologies are applied to solve complex project management challenges. Through detailed case studies, you will examine real-world scenarios where operations research techniques have been used to optimize project planning, resource allocation, and risk management. The module also delves into emerging trends and future directions, highlighting innovative approaches and advancements in both operations research and project management. By integrating theoretical knowledge with practical applications, you will gain a comprehensive understanding of how to leverage operations research to enhance project outcomes and address evolving industry demands.

### Learning Outcomes

By the end of this module, you should be able to:

- Describe fundamental concepts of mathematical programming in linear programming approaches.

- Demonstrate understanding of how linear programming methodologies are applied to solve optimization problems in economic contexts.

- Apply linear programming techniques to solve optimization problems encountered in economic scenarios.

- Critically analyze case studies and real-world applications of mathematical programming in economic policy analysis, identifying key insights and potential areas for improvement in decision-making processes

### Learning Activities/Task List

- Watch Lecture Video

- Review power presentation PDF

- Watch lecture related videos

- Complete participation assignment:  Quiz 1

- Complete personal introduction video

- Review concept assignments: Quiz 2

## INSTRUCTIONAL MATERIALS & LEARNING ACTIVITIES

Task 1: Go through the following notes:

Example 1.2.1

Problem: A construction company is tasked with completing a large residential building project. The project involves several activities, such as site preparation, foundation work, framing, plumbing, electrical installation, and finishing. The company has a limited number of workers and equipment, and it must complete the project within a tight deadline. The project manager needs to determine the optimal schedule and allocate resources efficiently to minimize costs while ensuring the project is completed on time.

Example 1.2.2

To solve this problem, the company can use the following Operations Research techniques:

- Critical Path Method (CPM)

- Linear Programming (LP) for Resource Allocation

1. Critical Path Method (CPM):

The Critical Path Method (CPM) is used to identify the sequence of critical activities that determine the overall project duration. These are the tasks that cannot be delayed without delaying the entire project.

##### Steps:

- List all activities: Identify each activity in the project along with their durations and dependencies.

- Network diagram: Construct a network diagram to map the flow of activities and dependencies.

- Calculate earliest and latest start/finish times: Determine the earliest and latest start/finish times for each activity.

- Identify the critical path: The critical path is the sequence of activities that have no slack (flexibility in start/finish times) and determines the project’s minimum completion time.

##### Application:

For the residential building project, the network of activities could be:

- A: Site preparation (5 days)

- B: Foundation work (10 days, starts after A)

- C: Framing (15 days, starts after B)

- D: Plumbing (8 days, starts after C)

- E: Electrical installation (7 days, starts after C)

- F: Finishing (12 days, starts after D and E)

##### Critical Path:

- The critical path is A → B → C → D → F, with a total duration of 50 days.

- Any delay in these activities will delay the entire project.

Solution:

- The project manager now knows the total time (50 days) needed to complete the project and which activities to prioritize to avoid delays.

2. Linear Programming (LP) for Resource Allocation:

To efficiently allocate resources (workers and equipment), the company uses Linear Programming (LP) to minimize labor and equipment costs subject to time constraints.

##### Problem Formulation:

Let:

- x1​ = Number of workers assigned to task A (Site preparation)

- x2 = Number of workers assigned to task B (Foundation work)

- ...

- c1,c2,...,c6​ = Costs of resources for tasks A, B, ..., F

Objective function: Minimize the total cost:

Minimize Z=c1x1+c2x2+...+c6x6​

Subject to:

- Time constraints for completing each activity (must complete activities within the given time for critical path)

- Resource availability constraints (workers and equipment)

##### Application:

Assume the following resource costs and availability for workers and equipment:

| Task | Required Workers | Cost per Worker per Day ($) | Duration (Days) |
| --- | --- | --- | --- |
| A: Site Prep | 5 | 100 | 5 |
| B: Foundation | 8 | 120 | 10 |
| C: Framing | 10 | 150 | 15 |
| D: Plumbing | 4 | 130 | 8 |
| E: Electrical | 6 | 140 | 7 |
| F: Finishing | 7 | 160 | 12 |

The LP model helps the company determine the optimal number of workers and allocation across the different tasks, ensuring project deadlines are met without exceeding the budget.

##### Solution:

Using an LP solver, the company finds the optimal resource allocation:

- Allocate 5 workers to Site Preparation (A), costing $500 per day for 5 days.

- Allocate 8 workers to Foundation (B), costing $960 per day for 10 days.

- Allocate 10 workers to Framing (C), and so on.

The solution gives the minimum total cost while ensuring that all tasks are completed within their required time.

### Emerging Trends and Future Directions

#### a) Artificial Intelligence (AI) for Predictive Project Management

AI and machine learning are revolutionizing project management by predicting project risks, resource needs, and deadlines more accurately. AI can be combined with operations research techniques to optimize resource allocation, predict cost overruns, and identify critical project bottlenecks.

Example: A construction firm uses AI to analyze past project data, helping it forecast potential delays in future projects. AI tools use historical data to predict which tasks are most likely to overrun their budgets, allowing project managers to adjust schedules and resources proactively.

#### b) Big Data Analytics for Real-time Decision-making

With the integration of big data, project managers can now make real-time decisions based on large amounts of project data. Operations research tools are used to analyze this data and adjust project plans accordingly.

Example: In large infrastructure projects, sensors and IoT devices monitor construction progress in real-time. This data is fed into operations research models to track performance and predict when delays might occur.

#### c) Blockchain for Transparent Project Management

Blockchain technology is emerging as a tool for ensuring transparency in project management. By using blockchain, project contracts and resource transactions can be recorded in a tamper-proof way, ensuring accountability and reducing disputes.

Example: In a construction project, blockchain is used to track payments and project milestones. As each milestone is completed, payments are automatically released, and all transactions are recorded on a blockchain ledger, reducing the risk of fraud or mismanagement.

#### MASTERY EXERCISE 1.1

Task 2: Attempt the following questions:

A software development company is managing a project with multiple interdependent tasks. The project has a limited number of developers and testers, and the project manager wants to minimize the total project cost while ensuring the project is completed within the deadline of 40 days.

The project consists of the following tasks:

| Task | Duration (days) | Preceding Task(s) | Required Developers | Cost per Developer per Day ($) |
| --- | --- | --- | --- | --- |
| A: Design | 8 | - | 3 | 200 |
| B: Coding | 10 | A | 5 | 250 |
| C: Testing | 7 | B | 4 | 220 |
| D: Review | 5 | C | 2 | 150 |
| E: Deployment | 4 | D | 3 | 180 |

a) Use the Critical Path Method (CPM) to determine the critical path and the total project duration.

b) Formulate a Linear Programming (LP) model to minimize the total cost of the project subject to the constraints of task durations and resource availability.

c) Discuss one emerging trend in operations research that could further optimize the project management process, and explain how it could be applied in this scenario.

|  | #### PRE-RECORDED LECTURE ON TOPIC |
| --- | --- |

Task 3: Listen to this Video on Operations Research in Real-world Project Management

[Slide 1: Introduction]

Speaker: Welcome to today's lecture on Operations Research (OR) in Real-world Project Management. Today, we will explore how OR techniques are applied in project management to optimize resources, reduce costs, and meet project timelines. We'll also discuss emerging trends that are shaping the future of project management, such as Artificial Intelligence (AI) and Big Data.

[Slide 2: Overview]

Speaker: Let's start with a brief overview of today's topics:

- What is Operations Research?

- Key OR Techniques in Project Management

- Real-world Case Studies and Applications

- Emerging Trends in OR and Project Management

- Future Directions and Conclusion

### [Slide 3: What is Operations Research?]

Speaker: Operations Research is a discipline that uses mathematical models, statistics, and algorithms to aid in decision-making. In project management, OR helps us solve complex problems related to scheduling, resource allocation, cost minimization, and risk management.

Key Objectives in OR:

- Optimize the use of resources (like workers, equipment, or money)

- Minimize costs while adhering to project constraints

- Meet deadlines without compromising quality

### [Slide 4: Key Operations Research Techniques in Project Management]

Speaker: Some common Operations Research techniques used in project management include:

- Critical Path Method (CPM): Identifies the sequence of activities that determine the overall project duration.

- Program Evaluation Review Technique (PERT): Used for projects where task durations are uncertain, often incorporating probabilities.

- Linear Programming (LP): Helps minimize or maximize a certain objective, like cost or time, subject to resource constraints.

- Queuing Theory: Used to optimize workflows and minimize waiting times in resource-constrained environments.

These techniques form the backbone of efficient project management and help solve many real-world problems.

### [Slide 5: Case Study - Construction Project Scheduling]

Speaker: Let’s now dive into a real-world case study.

Case Study: Construction Project Scheduling

Imagine a company is managing a large construction project. The tasks include site preparation, foundation work, framing, plumbing, and electrical installation. The company faces tight deadlines, limited workers, and high costs.

How do they optimize project scheduling and resource allocation to finish on time and within budget?

### [Slide 6: Applying Critical Path Method (CPM)]

Speaker: The Critical Path Method (CPM) is used to identify the longest sequence of dependent tasks—known as the critical path. Any delay in the critical path delays the entire project.

Here’s how CPM helps:

- Identify tasks and dependencies: First, we list all the tasks and their dependencies.

- Create a network diagram: This shows the flow and interrelationships between tasks.

- Calculate earliest and latest start/finish times: For each task, we calculate when it should start and end.

- Determine the critical path: This is the longest path through the network with no slack.

### [Slide 7: Real-world Solution using CPM]

Speaker: In our construction project, the critical path might be: Site Preparation → Foundation → Framing → Plumbing → Finishing.

With CPM, we identify the critical activities and focus our resources to ensure these tasks don’t get delayed. This helps us complete the project in the shortest time possible, for example, 45 days.

If non-critical tasks—like landscaping—are delayed, it won’t impact the overall project timeline.

### [Slide 8: Resource Allocation using Linear Programming (LP)]

Speaker: Next, we use Linear Programming (LP) to allocate resources efficiently. The company has a limited budget and workforce, so LP helps answer questions like:

- How many workers should we assign to each task?

- How can we minimize costs while still finishing the project on time?

Objective Function: Minimize costs, subject to time and resource constraints.

### [Slide 9: LP Solution in Construction Project]

Speaker: Let’s say the company needs 5 workers for foundation work, 10 for framing, and 8 for plumbing. The costs for each task vary, and we want to minimize labor costs while meeting the project deadline.

Using LP software, we can calculate the optimal number of workers to assign to each task, ensuring the project is completed at the lowest possible cost.

In this case, LP might show that assigning more workers to critical tasks like framing helps reduce the overall project duration and avoids penalties for late delivery.

### [Slide 10: Emerging Trends in Operations Research and Project Management]

Speaker: Now, let’s look at some emerging trends that are revolutionizing the application of Operations Research in project management.

- Artificial Intelligence (AI): AI can be used to predict project risks, allocate resources dynamically, and adapt to changing project conditions.

  - Example: AI algorithms analyze historical data to predict when specific tasks are likely to exceed their budgets, allowing managers to adjust resources proactively.

- Big Data Analytics: With large amounts of data generated during projects, Big Data helps identify patterns, optimize workflows, and predict delays.

  - Example: Sensors on a construction site provide real-time data, which is fed into an OR model to predict equipment downtime, helping project managers react faster.

- Blockchain Technology: Blockchain ensures transparency in transactions and contracts, especially in projects with multiple stakeholders.

  - Example: In a large infrastructure project, blockchain tracks payments and milestones, reducing disputes and ensuring all parties are accountable.

### [Slide 11: Future Directions in Operations Research and Project Management]

Speaker: The future of Operations Research in project management is bright. Here are a few directions to watch:

- AI-powered Project Management Tools: Future tools will combine OR models with AI to provide real-time optimization.

- Predictive Analytics: With more data available, predictive models will help forecast future risks and outcomes, giving project managers more control.

- Sustainability Optimization: OR will also be used to incorporate environmental impact into project decisions, helping organizations meet sustainability goals.

### [Slide 12: Conclusion]

Speaker: To sum up, Operations Research is essential in project management for solving complex problems related to time, cost, and resource optimization. Techniques like CPM and LP are already widely used in industries like construction, software development, and manufacturing. The integration of AI, Big Data, and Blockchain will further transform how we manage projects, making them more efficient, transparent, and adaptive to change.

### [Slide 13: Questions and Discussion]

Speaker: That brings us to the end of today's lecture. Thank you for your attention. I now open the floor to questions and discussions. Feel free to ask about the techniques, case studies, or emerging trends discussed today.

|  | #### VIDEO 3 (Youtube, please include link) |
| --- | --- |

Task 4: Here is a video on “Real World Applications of Operations Research”. The video is 7.24 mins; click the link below and listen.

https://youtu.be/flsR_fUbJtk?si=HICp9MC-UE-1FFCq

Having listened to the video, attempt the following:

Quiz:

Based on the knowledge gained in Operations Research in Real-world Project Management, propose a real-world application where you utilize OR techniques to solve a project management challenge.

## REFERENCE LIST AND FURTHER READING

- Law, A. M. (2015). Simulation modeling and analysis (5th ed.). McGraw-Hill Education.

- Rubinstein, R. Y., & Kroese, D. P. (2016). Simulation and the Monte Carlo method (2nd ed.). Wiley.

- Banks, J., Carson, J. S., Nelson, B. L., & Nicol, D. M. (2010). Discrete-event system simulation (5th ed.). Pearson.

- Hillson, D. (2017). Practical project risk management: The ATOM methodology (3rd ed.). Management Concepts.

- Hillson, D. (2017). Practical project risk management: The ATOM methodology (3rd ed.). Management Concepts.

- Smith, N. J. (2014). Managing risk in construction projects (2nd ed.). Wiley-Blackwell.

### END OF MODULE ASSESSMENT 1.10

Task 5: Attempt all the questions:

A construction company is managing three major projects (A, B, and C). The company has limited resources in terms of budget and labor hours and wants to maximize its total profit. The budget available is $1.5 million, and the total labor hours available are 10,000. Each project has an associated cost, required labor hours, and expected profit as detailed below:

| Project | Cost ($ million) | Labor hours | Profit ($ million) |
| --- | --- | --- | --- |
| A | 0.6 | 4,000 | 0.9 |
| B | 0.8 | 5,000 | 1.2 |
| C | 0.4 | 2,000 | 0.7 |

The company can only fully execute a project, meaning partial work on any project is not allowed. The company seeks to maximize its profit while staying within its budget and labor hour limits.

- Formulate this as a binary integer programming problem (2marks)

- Solve it to determine which projects should be selected to maximize profit (3marks)

Rubrics

#### Step 1: Define Decision Variables

Let xA,xB,xC​ be binary decision variables where:

xi1        If project i is selected 0 If project i is not selected ​

Thus, xA, xB, xC∈{0,1} correspond to the selection of Projects A, B, and C.

#### Step 2: Objective Function

The objective is to maximize the total profit, which is the sum of the profits for the selected projects:

Maximize Z=0.9xA+1.2xB+0.7xC

#### Step 3: Constraints

- Budget Constraint: The total cost of selected projects must not exceed the budget of $1.5 million:

0.6xA+0.8xB+0.4xC≤1.5

- Labor Hours Constraint: The total labor hours used by the selected projects must not exceed 10,000 hours:

4000xA+5000xB+2000xC≤10,000

- Binary Constraints: Each decision variable xA,xB,xC​ is binary:

xA,xB,xC∈{0,1}

#### Step 4: Solving the Problem

We can solve this binary integer programming problem using a solver (such as Excel Solver, Python’s PuLP library, or similar tools).

Solution:

- xA=1(Project A is selected)

- xC=1(Project C is selected)

- xB=0(Project B is not selected)

Thus, the company should select Projects A and C.

Total Profit:

Z=0.9(1)+0.7(1)=1.6 million dollarsZ = 0.9(1) + 0.7(1) = 1.6 million dollars

Total Cost:

0.6(1) + 0.4(1) = 1 \text{ million dollars} \quad (\text{within the $1.5 million budget})

Total Labor Hours:

4000(1)+2000(1)=6000 hours(within the 10,000 labor hours limit)

#### Conclusion:

The company should select Projects A and C to maximize profit while staying within the budget and labor hour constraints. This solution results in a total profit of $1.6 million.

## TAKE HOME MESSAGE/SELF REFLECTION

Task 6: After going through Introduction to Operations Research in Real-world Project Management, how can you apply this real-world life situations?

### WHAT’S NEXT?

- Done

- Urah!

- Move to Year Two Second First Semester